## HAZID Log
Structure No. | Structure Type | Spans | Structure Name | Carries | Material Type | Work Item | Possible Consequence | Current Risk |  |  |  | Risk Mitigation Proposals | Proposed Risk |  |  |  | Status | Detailed Exam Regime (yrs) | Last Exam | Next Exam
[8 empty] | Liklihood | Severity | Rating | Date Logged |  | Liklihood | Severity | Rating | Proposed Completion
DAE2/XX | UB | 1 | Broken Banks Culvert | Rail over water | Masonry | Fractures | Loss of strength | 2 | 2 | 4 | 2021-11-29 | Repointing and tabbing | 1 | 2 | 2 | 1 year | Open | 12 | 2021-11-29 | 2033-11-26
DAE2/XX | UB | 1 | Broken Banks Culvert | Rail over water | Masonry | Spalled masonry | Loss of strength | 2 | 1 | 2 | 2021-11-29 | Recasing | 1 | 1 | 1 | 1 year | Open
DAE2/XX | UB | 1 | Broken Banks Culvert | Rail over water | Masonry | Open joints | Loss of mortar, loss of strength | 2 | 1 | 2 | 2021-11-29 | Repointing | 1 | 1 | 1 | 1 year | Open
DAE2/XX | UB | 1 | Broken Banks Culvert | Rail over water | Masonry | Collapsed retaining wall | Risk of further collapse and strcutural instability | 2 | 1 | 2 | 2021-11-29 | Rebuild retainging wall | 1 | 1 | 1 | 6 months | Open
DAE2/XX | UB | 1 | Broken Banks Culvert | Rail over water | Masonry | Apron undercutting | Scour and collaspe of the apron and retaining walls | 2 | 2 | 4 | 2021-11-29 | Monitor and repair | 1 | 2 | 2 | Ongoing | Open
DAE2/XX | UB | 1 | Broken Banks Culvert | Rail over water | Masonry | Debris buildup | Blocked culvert and upstream flooding | 1 | 2 | 2 | 2021-11-29 | Debris removal | 1 | 2 | 2 | 3 months | Open
DAE2/XX | UB | 1 | Broken Banks Culvert | Rail over water | Masonry | Collapsed headwall | Risk of further collapse and structural instability | 2 | 2 | 4 | 2021-11-29 | Monitor and rebuild headwall | 1 | 2 | 2 | 6 months | Open
DAE2/11A | UB | 1 | Etherly Dene Culvert | Rail over water | Masonry | Spalled and missing masonry | Loss of strength | 2 | 2 | 4 | 2021-11-29 | Recasing | 1 | 2 | 2 | 1 year | Open | 12 | 2021-11-29 | 2033-11-26
DAE2/11A | UB | 1 | Etherly Dene Culvert | Rail over water | Masonry | Debris buildup | Blocked culvert and upstream flooding | 1 | 2 | 2 | 2021-11-29 | Debris removal | 1 | 2 | 2 | 3 months | Open
DAE2/11A | UB | 1 | Etherly Dene Culvert | Rail over water | Masonry | Open joints | Loss of strength | 2 | 1 | 2 | 2021-11-29 | Repointing | 1 | 1 | 1 | 1 year | Open
DAE2/11A | UB | 1 | Etherly Dene Culvert | Rail over water | Masonry | Displaced slab | Collapse | 2 | 1 | 2 | 2021-11-29 | Monitor and replace if necessary | 1 | 1 | 1 | Ongoing | Open
DAE2/16 | OB | 2 | Woodside Farm Bridge | Farm access over rail | Metallic/Timber | Entire deck is rotten/loose | People falling through deck/deck falling on to trains | 3 | 4 | 12 | 2021-08-27 | The structure has restricted access | 1 | 4 | 4 | Immediately | Open | 1 | 2021-08-27 | 2022-08-27
DAE2/18 | UB | 1 | Paradise – Witton Park | Rail over road | Metallic | Open joints | Loss of mortar, loss of strength | 3 | 1 | 3 | 2021-08-27 | Repointing | 1 | 1 | 1 | 1 year | Open | 6 | 2021-08-27 | 2027-08-26
DAE2/18 | UB | 1 | Paradise – Witton Park | Rail over road | Metallic | Fractures | Loss of strength | 3 | 2 | 6 | 2021-08-27 | Repoint and tabbing | 1 | 2 | 2 | 6 months | Open
DAE2/18 | UB | 1 | Paradise – Witton Park | Rail over road | Metallic | Bulging | Void or displaced material behind the arch | 3 | 2 | 6 | 2021-08-27 | Regular monitoring | 2 | 2 | 4 | Ongoing | Open
DAE2/18 | UB | 1 | Paradise – Witton Park | Rail over road | Metallic | Section loss to the deck | Loss of strength | 4 | 1 | 4 | 2021-08-27 | Clean and paint | 2 | 1 | 2 | 6 months | Open
DAE2/18 | UB | 1 | Paradise – Witton Park | Rail over road | Metallic | Broken handrail | Worker falling from height | 2 | 3 | 6 | 2021-08-27 | Repair handrail | 1 | 3 | 3 | 1 month | Open
DAE2/18A | UB | 1 | Witton Park Culvert | Rail over water | Masonry | Missing brickwork (Downstream Headwall) | Collapse and buildup affecting railway section | 2 | 4 | 8 | 2023-01-30 | Repair headwall | 1 | 4 | 4 | 1 year | Open | 6 | Unknown | 2024-01-30
DAE2/18A | UB | 1 | Witton Park Culvert | Rail over water | Masonry | Unexamined sections | Unknown defects throughout | 3 | 4 | 12 | 2023-01-30 | Undertake full detailed exam | 1 | 4 | 4 | 1 year | Open
DAE2/19 | UB | 5 | Etherley Viaduct | Rail over water and road | Masonry | Spalled and missing brickwork | Loss of strength | 2 | 3 | 6 | 2021-08-27 | Recasing | 1 | 3 | 3 | 6 months | Open | 12 | 2021-08-27 | 2033-08-24
DAE2/19 | UB | 5 | Etherley Viaduct | Rail over water and road | Masonry | Vegetation obscurring elements | Loss of strength due to roots causing damage Unable to view possible defects under vegetation | 3 | 1 | 3 | 2021-08-27 | Vegetation removal | 1 | 1 | 1 | 6 months | Open
DAE2/19 | UB | 5 | Etherley Viaduct | Rail over water and road | Masonry | Fractures | Loss of strength | 3 | 2 | 6 | 2021-08-27 | Repointing and tabbing | 1 | 2 | 2 | 6 months | Open
DAE2/20 | UB | 1 | Slotburn | Rail over road | Masonry | Fractures | Significant fractures causing loss of strength | 3 | 3 | 9 | 2021-08-27 | Repointing and tabbing | 2 | 3 | 6 | 3 months | Open | 6 | 2021-08-27 | 2027-08-26
DAE2/20 | UB | 1 | Slotburn | Rail over road | Masonry | Spalling | Deep spalling causing loss of strength | 3 | 2 | 6 | 2021-08-27 | Recasing | 1 | 2 | 2 | 6 months | Open
DAE3/2 | UB | 1 | Enginerman's Cottage | Rail over water | Masonry | Open joints | Loss of mortar, loss of strength | 2 | 1 | 2 | 2021-11-29 | Repointing | 1 | 1 | 1 | 6 months | Open | 12 | 2021-11-29 | 2033-11-26
DAE3/2 | UB | 1 | Enginerman's Cottage | Rail over water | Masonry | Spalled, loose and missing masonry | Loss of strength, possible collapse | 2 | 2 | 4 | 2021-11-29 | Recasing | 1 | 2 | 2 | 3 months | Open
DAE3/2 | UB | 1 | Enginerman's Cottage | Rail over water | Masonry | Fractures | Loss of strength | 3 | 2 | 6 | 2021-11-29 | Repointing and tabbing | 1 | 2 | 2 | 6 months | Open
DAE3/2 | UB | 1 | Enginerman's Cottage | Rail over water | Masonry | Collapsed wingwall | Risk of further collapse and structural instability | 3 | 2 | 6 | 2021-11-29 | Rebuild wingwall | 1 | 2 | 2 | 1 month | Open
DAE3/2 | UB | 1 | Enginerman's Cottage | Rail over water | Masonry | Scoured riverbed and debris buildup | Structural instability, blocked culvert and upstream flooding | 2 | 3 | 6 | 2021-11-29 | Infill scour hole and remove debris | 1 | 3 | 3 | 3 months | Open
DAE3/3A | UB | 1 | Nature Reserve | Rail over water | Masonry | Fractures | Loss of strength | 2 | 2 | 4 | 2021-11-29 | Repointing and tabbing | 1 | 2 | 2 | 3 months | Open | 12 | 2021-11-29 | 2033-11-26
DAE3/3A | UB | 1 | Nature Reserve | Rail over water | Masonry | Open joints | Loss of mortar, loss of strength | 2 | 1 | 2 | 2021-11-29 | Repointing | 1 | 1 | 1 | 6 months | Open
DAE3/3A | UB | 1 | Nature Reserve | Rail over water | Masonry | Spalled and missing masonry | Loss of strength | 2 | 2 | 4 | 2021-11-29 | Recasing | 1 | 2 | 2 | 6 months | Open
DAE3/4 | UB | 1 | Clemmy Bank | Rail over road | Masonry | Fractures | Loss of strength | 3 | 2 | 6 | 2021-08-27 | Repointing and tabbing | 1 | 2 | 2 | 6 months | Open | 12 | 2021-08-27 | 2033-08-24
DAE3/4 | UB | 1 | Clemmy Bank | Rail over road | Masonry | Spalling | Loss of strength | 2 | 2 | 4 | 2021-08-27 | Recasing | 1 | 2 | 2 | 6 months | Open
DAE3/5 | UB | 1 | Low Garth Bridge | Rail over farm access | Masonry | Spalling and loose stonework | Loss of strength | 3 | 2 | 6 | 2021-08-27 | Recasing | 1 | 2 | 2 | 6 months | Open | 12 | 2021-08-27 | 2033-08-24
DAE3/5 | UB | 1 | Low Garth Bridge | Rail over farm access | Masonry | Fractures | Loss of strength | 3 | 2 | 6 | 2021-08-27 | Repointing and tabbing | 1 | 2 | 2 | 6 months | Open
DAE3/5 | UB | 1 | Low Garth Bridge | Rail over farm access | Masonry | Bulging | Void or displaced material behind Wingwall, risk of collapse | 2 | 3 | 6 | 2021-08-27 | Regular monitoring | 1 | 3 | 3 | Ongoing | Open
DAE3/5A | UB | 1 | Witton-le-Wear | Rail over water | Masonry | Fractures | Loss of strength | 2 | 2 | 4 | 2021-11-29 | Repointing and tabbing | 1 | 2 | 2 | 6 months | Open | 12 | 2021-11-29 | 2033-11-26
DAE3/5A | UB | 1 | Witton-le-Wear | Rail over water | Masonry | Spalled and missing masonry | Loss of strength | 2 | 2 | 4 | 2021-11-29 | Recasing | 1 | 2 | 2 | 6 months | Open
DAE3/5A | UB | 1 | Witton-le-Wear | Rail over water | Masonry | Silt and debris buildup | Blocked culvert and upstream flooding | 2 | 1 | 2 | 2021-11-29 | Debris removal | 1 | 1 | 1 | 3 months | Open
DAE3/7 | UB | 1 | Chapman Hill Culvert | Rail over water | Masonry | Spalled masonry | Loss of strength | 2 | 1 | 2 | 2021-11-29 | Recasing | 1 | 1 | 1 | 6 months | Open | 12 | 2021-11-29 | 2033-11-26
DAE3/7 | UB | 1 | Chapman Hill Culvert | Rail over water | Masonry | Fractures | Loss of strength | 3 | 2 | 6 | 2021-11-29 | Repointing and tabbing | 1 | 2 | 2 | 6 months | Open
DAE3/7 | UB | 1 | Chapman Hill Culvert | Rail over water | Masonry | Open joints | Loss of mortar, loss of strength | 2 | 1 | 2 | 2021-11-29 | Repointing | 1 | 1 | 1 | 6 months | Open
DAE3/8 | UB | 1 | McNeil’s Bridge | Rail over farm access | Masonry | Fractures | Loss of strength to arch | 3 | 3 | 9 | 2021-08-27 | Repointing and tabbing | 1 | 3 | 3 | 6 months | Open | 6 | 2021-08-27 | 2027-08-26
DAE3/8 | UB | 1 | McNeil’s Bridge | Rail over farm access | Masonry | Loss of mortar | Loss of strength | 2 | 2 | 4 | 2021-08-27 | Repointing | 1 | 2 | 2 | 1 year | Open
DAE3/9 | UB | 1 | Wadley Beck | Rail over water | Masonry | Spalling, loose and missing masonry | Loss of strength | 2 | 2 | 4 | 2021-11-29 | Recasing | 1 | 2 | 2 | 1 year | Open | 12 | 2021-11-29 | 2033-11-26
DAE3/9 | UB | 1 | Wadley Beck | Rail over water | Masonry | Open joints | Loss of mortar, loss of strength | 2 | 1 | 2 | 2021-11-29 | Repointing | 1 | 1 | 1 | 1 year | Open
DAE3/9 | UB | 1 | Wadley Beck | Rail over water | Masonry | Displaced masonry | Collapse | 2 | 2 | 4 | 2021-11-29 | Recasing and monitor | 1 | 2 | 2 | Ongoing | Open
DAE3/9 | UB | 1 | Wadley Beck | Rail over water | Masonry | Rotten timbers | Collapse of retaining wall | 2 | 1 | 2 | 2021-11-29 | Replace timbers | 1 | 1 | 1 | 3 months | Open
DAE3/10 | UB | 1 | Low Shipley Culvert | Rail over water | Masonry | Debris buildup | Blocked culvert and upstream flooding | 1 | 3 | 3 | 2021-11-29 | Debris removal | 1 | 3 | 3 | 3 months | Open | 12 | 2021-11-29 | 2033-11-26
DAE3/10 | UB | 1 | Low Shipley Culvert | Rail over water | Masonry | Spalled and missing masonry | Loss of strength | 2 | 2 | 4 | 2021-11-29 | Recasing | 1 | 2 | 2 | 1 year | Open
DAE3/10 | UB | 1 | Low Shipley Culvert | Rail over water | Masonry | Open joints | Loss of mortar, loss of strength | 2 | 1 | 2 | 2021-11-29 | Repointing | 1 | 1 | 1 | 1 year | Open
DAE3/11 | UB | 1 | Low Shipley No2 | Rail over water | AMCO pipe/masonry | Missing brickwork | Loss of strength | 1 | 1 | 1 | 2021-11-29 | Recasing | 1 | 1 | 1 | 5 years | Open | 12 | 2021-11-29 | 2033-11-26
DAE3/11A | UB | 1 | Harperly Hall | Rail over water | Masonry | Open joints | Loss of mortar, loss of strength | 2 | 1 | 2 | 2021-11-29 | Repointing | 1 | 1 | 1 | 1 year | Open | 12 | 2021-11-29 | 2033-11-26
DAE3/11A | UB | 1 | Harperly Hall | Rail over water | Masonry | Missing masonry | Loss of strength | 2 | 3 | 6 | 2021-11-29 | Monitoring and rebuild | 1 | 3 | 3 | 1 year | Open
DAE3/11A | UB | 1 | Harperly Hall | Rail over water | Masonry | Spalled, loose and missing masonry | Loss of strength | 2 | 2 | 4 | 2021-11-29 | Recasing | 1 | 2 | 2 | 1 year | Open
DAE3/11A | UB | 1 | Harperly Hall | Rail over water | Masonry | Debris buildup | Blocked culvert and upstream flooding | 2 | 2 | 4 | 2021-11-29 | Debric removal | 1 | 2 | 2 | 1 year | Open
DAE3/11A | UB | 1 | Harperly Hall | Rail over water | Masonry | Fractures | Loss of strength | 2 | 2 | 4 | 2021-11-29 | Repointing | 1 | 2 | 2 | 1 year | Open
DAE3/11A | UB | 1 | Harperly Hall | Rail over water | Masonry | Displaced masonry | Collapse | 2 | 2 | 4 | 2021-11-29 | Recasing | 1 | 2 | 2 | 3 months | Open
DAE3/12 | UB | 1 | Harperley Station Bridge – Low Harperley | Rail over water | Metallic | Corrosion | Loss of strength to deck | 3 | 2 | 6 | 2021-08-27 | Clean and paint | 1 | 2 | 2 | 6 months | Open | 6 | 2021-08-27 | 2027-08-26
DAE3/12 | UB | 1 | Harperley Station Bridge – Low Harperley | Rail over water | Metallic | Loss of mortar | Loss of strength | 2 | 2 | 4 | 2021-08-27 | Repointing | 1 | 2 | 2 | 1 year | Open
DAE3/12 | UB | 1 | Harperley Station Bridge – Low Harperley | Rail over water | Metallic | Displacement of wingwall | Possible collapse | 2 | 3 | 6 | 2021-08-27 | Monitoring and repointing | 1 | 3 | 3 | Ongoing | Open
DAE3/12 | UB | 1 | Harperley Station Bridge – Low Harperley | Rail over water | Metallic | Vegetation | Loss of strength due to roots causing damage Unable to view possible defects under vegetation | 3 | 1 | 3 | 2021-08-27 | Vegetation removal | 1 | 1 | 1 | 6 months | Open
DAE3/12 | UB | 1 | Harperley Station Bridge – Low Harperley | Rail over water | Metallic | Rotting timber deck | Workers falling through deck | 2 | 2 | 4 | 2021-08-27 | Replace rotten timbers | 1 | 2 | 2 | 3 months | Open
DAE3/13 | UB | 1 | Eels Beck – Thornley Beck | Rail over water | Masonry | Loose spalled and missing stonework | Loss of strength to arch | 3 | 4 | 12 | 2021-08-27 | Recasing | 1 | 4 | 4 | 3 months | Open | 6 | 2021-08-27 | 2027-08-26
DAE3/13 | UB | 1 | Eels Beck – Thornley Beck | Rail over water | Masonry | Fractures | Loss of strength to arch | 3 | 3 | 9 | 2021-08-27 | Repointing an tabbing | 1 | 3 | 3 | 3 months | Open
DAE3/13 | UB | 1 | Eels Beck – Thornley Beck | Rail over water | Masonry | Bulging | Void or displaced material behind the arch | 2 | 3 | 6 | 2021-08-27 | Monitor regularly | 1 | 3 | 3 | Ongoing | Open
DAE3/14 | UB | 1 | Bradley Beck – Bradley Burn | Rail over water | Metallic | Fractures | Loss of strength | 2 | 2 | 4 | 2021-08-27 | Repointing and tabbing | 1 | 2 | 2 | 6 months | Open | 6 | 2021-08-27 | 2027-08-26
DAE3/14 | UB | 1 | Bradley Beck – Bradley Burn | Rail over water | Metallic | Spalled and missing stonework | Loss of strength | 2 | 2 | 4 | 2021-08-27 | Recasing | 1 | 2 | 2 | 6 months | Open
DAE3/14 | UB | 1 | Bradley Beck – Bradley Burn | Rail over water | Metallic | Undercutting to the training walls | Collapse of wall | 2 | 2 | 4 | 2021-08-27 | Rock armour or concrete bagwork | 2 | 2 | 4 | 6 months | Open
DAE3/14 | UB | 1 | Bradley Beck – Bradley Burn | Rail over water | Metallic | Spalling to the concrete | Loss of strength and corrosion to the encased metal | 2 | 3 | 6 | 2021-08-27 | Concrete repairs | 1 | 3 | 3 | 6 months | Open
DAE3/14 | UB | 1 | Bradley Beck – Bradley Burn | Rail over water | Metallic | Rotten ballast timbers | Loss of ballast from the track bed in to the watercourse below | 3 | 2 | 6 | 2021-08-27 | Replace timbers | 1 | 2 | 2 | 3 months | Open
DAE3/14A | UB | 1 | Scotch Isle Farm | Rail over water | Masonry | Spalled, loose and missing masonry | Loss of strength | 2 | 2 | 4 | 2021-11-29 | Recasing | 1 | 2 | 2 | 1 year | Open | 12 | 2021-11-29 | 2033-11-26
DAE3/14A | UB | 1 | Scotch Isle Farm | Rail over water | Masonry | Debris buildup | Blocked culvert and upstream flooding | 2 | 1 | 2 | 2021-11-29 | Debris removal | 1 | 1 | 1 | 6 months | Open
DAE3/14A | UB | 1 | Scotch Isle Farm | Rail over water | Masonry | Displaced masonry | Collapse | 2 | 2 | 4 | 2021-11-29 | Monitoring and recasing | 1 | 2 | 2 | 6 months | Open
DAE3/14A | UB | 1 | Scotch Isle Farm | Rail over water | Masonry | Vegetation | Loss of strength due to roots causing damage Unable to view possible defects under vegetation | 1 | 2 | 2 | 2021-11-29 | Monitoring and vegetation removal | 1 | 2 | 2 | 6 months | Open
DAE3/15 | UB | 5 | Wolsingham Viaduct | Rail over water | Metallic | Open joints | Loss of strength | 2 | 1 | 2 | 2021-08-27 | Repointing | 1 | 1 | 1 | 1 year | Open | 6 | 2021-08-27 | 2027-08-26
DAE3/15 | UB | 5 | Wolsingham Viaduct | Rail over water | Metallic | Fractures | Loss of strength | 3 | 2 | 6 | 2021-08-27 | Repointing and tabbing | 1 | 2 | 2 | 6 months | Open
DAE3/15 | UB | 5 | Wolsingham Viaduct | Rail over water | Metallic | Spalled stonework | Loss of strength | 2 | 2 | 4 | 2021-08-27 | Recasing | 1 | 2 | 2 | 6 months | Open
DAE3/15 | UB | 5 | Wolsingham Viaduct | Rail over water | Metallic | Undercutting to 2No wingwalls | Risk of collapse | 2 | 3 | 6 | 2021-08-27 | Rock armour or concrete bagwork | 1 | 3 | 3 | 3 months | Open
DAE3/15 | UB | 5 | Wolsingham Viaduct | Rail over water | Metallic | Debris build up | Can cause scour around the base of Piers | 2 | 3 | 6 | 2021-08-27 | Debris clearance | 1 | 3 | 3 | 1 month | Open
DAE3/15 | UB | 5 | Wolsingham Viaduct | Rail over water | Metallic | Corrosion and LOS to deck | Loss of strength to deck | 2 | 3 | 6 | 2021-08-27 | Clean and paint | 1 | 3 | 3 | 6 months | Open
DAE3/15 | UB | 5 | Wolsingham Viaduct | Rail over water | Metallic | Broken handrail section | Worker falling | 2 | 3 | 6 | 2021-08-27 | Replace section | 1 | 3 | 3 | 1 month | Open
DAE3/18 | UB | 1 | Ashes Beck – Ashes House | Rail over water | Metallic | Corrosion and pitting | Loss of strength to deck | 2 | 3 | 6 | 2021-08-27 | Clean and paint | 1 | 3 | 3 | 6 months | Open | 6 | 2021-08-27 | 2027-08-26
DAE3/18 | UB | 1 | Ashes Beck – Ashes House | Rail over water | Metallic | Undermining of the Abutment | Collapse of the Abutment | 2 | 4 | 8 | 2021-08-27 | Rock armour or concrete bagwork | 1 | 4 | 4 | 3 months | Open
DAE3/18 | UB | 1 | Ashes Beck – Ashes House | Rail over water | Metallic | Vegetation | Loss of strength due to roots causing damage Unable to view possible defects under vegetation | 2 | 1 | 2 | 2021-08-27 | Vegetation removal | 1 | 1 | 1 | 6 months | Open
DAE3/19 | UB | 1 | Holebeck – Harelaw | Rail over water | Metallic | Rotting longitudinal timbers | Rails could become unstable | 2 | 4 | 8 | 2021-08-27 | Replace rotten timbers | 1 | 4 | 4 | 3 months | Open | 6 | 2021-08-27 | 2027-08-26
DAE3/19 | UB | 1 | Holebeck – Harelaw | Rail over water | Metallic | Fractured bedstone | Supports main girder which could start hammering | 2 | 3 | 6 | 2021-08-27 | Repoint and tab | 1 | 3 | 3 | 3 months | Open
DAE3/19 | UB | 1 | Holebeck – Harelaw | Rail over water | Metallic | Corrosion and pitting to deck | Loss of strength to deck | 2 | 2 | 4 | 2021-08-27 | Clean and paint | 1 | 2 | 2 | 6 months | Open
DAE3/19 | UB | 1 | Holebeck – Harelaw | Rail over water | Metallic | Timber deck rotting | Workers falling through deck | 2 | 2 | 4 | 2021-08-27 | Replace rotten timbers | 1 | 2 | 2 | 3 months | Open
DAE3/19 | UB | 1 | Holebeck – Harelaw | Rail over water | Metallic | Displaced stonework to training walls | Collapse | 2 | 2 | 4 | 2021-08-27 | Repoint and monitor | 1 | 2 | 2 | 6 months | Open
DAE3/20 | UB | 2 | Bollihope Burn | Rail over water | Concrete | Fractures | Loss of strength | 3 | 2 | 6 | 2021-08-27 | Repoint and tab | 1 | 2 | 2 | 6 months | Open | 12 | 2021-08-27 | 2033-08-24
DAE3/20 | UB | 2 | Bollihope Burn | Rail over water | Concrete | Bulging | Void or displaced material behind, risk of collapse | 2 | 3 | 6 | 2021-08-27 | Regular monitoring | 2 | 3 | 6 | Ongoing | Open
DAE3/20 | UB | 2 | Bollihope Burn | Rail over water | Concrete | Spalled stonework | Loss of strength | 2 | 2 | 4 | 2021-08-27 | Recasing | 1 | 2 | 2 | 6 months | Open
DAE3/20 | UB | 2 | Bollihope Burn | Rail over water | Concrete | Spalled concrete, looks to be purposefully removed | Loss of strength, exposes metal to air, risk of corrosion | 2 | 2 | 4 | 2021-08-27 | Repair concrete | 1 | 2 | 2 | 6 months | Open
DAE3/20 | UB | 2 | Bollihope Burn | Rail over water | Concrete | Missing handrail section | Worker falling | 2 | 3 | 6 | 2021-08-27 | Replace section | 1 | 3 | 3 | 1 month | Open
DAE3/21 | UB | 4 | Broadwood Bridge | Rail over water | Metallic | Fractures | Loss of strength | 2 | 3 | 6 | 2021-08-27 | Repointing and tabbing | 1 | 3 | 3 | 6 months | Open | 6 | 2021-08-27 | 2027-08-26
DAE3/21 | UB | 4 | Broadwood Bridge | Rail over water | Metallic | Spalled and missing stonework | Loss of strength | 2 | 3 | 6 | 2021-08-27 | Recasing | 1 | 3 | 3 | 6 months | Open
DAE3/21 | UB | 4 | Broadwood Bridge | Rail over water | Metallic | Vegetation | Loss of strength due to roots causing damage Unable to view possible defects under vegetation | 2 | 1 | 2 | 2021-08-27 | Vegetation removal | 1 | 1 | 1 | 6 months | Open
DAE3/21 | UB | 4 | Broadwood Bridge | Rail over water | Metallic | Corrosion and loss of section | Loss of strength to the deck | 2 | 3 | 6 | 2021-08-27 | Clean and paint | 1 | 3 | 3 | 6 months | Open
DAE3/22A | UB | 1 | Bridge End Culvert | Rail over water | Masonry/gabions | Corrosion | Loss of strength to soffit | 2 | 1 | 2 | 2021-11-29 | Clean and paint or apply linseed oil | 2 | 1 | 2 | 5 years | Open | 12 | 2021-11-29 | 2033-11-26
DAE3/22A | UB | 1 | Bridge End Culvert | Rail over water | Masonry/gabions | Open joints | Loss of mortar, loss of strength | 2 | 1 | 2 | 2021-11-29 | Repointing | 1 | 1 | 1 | 1 year | Open
DAE3/22A | UB | 1 | Bridge End Culvert | Rail over water | Masonry/gabions | Missing masonry | Loss of strength | 2 | 2 | 4 | 2021-11-29 | Recasing | 1 | 2 | 2 | 1 year | Open
DAE3/22A | UB | 1 | Bridge End Culvert | Rail over water | Masonry/gabions | Missing and displaced slabs | Collapse, loss of strength | 2 | 2 | 4 | 2021-11-29 | Monitor and recase | 1 | 2 | 2 | 6 months | Open
DAE3/22A | UB | 1 | Bridge End Culvert | Rail over water | Masonry/gabions | Debris buildup | Blocked culvert and upstream flooding | 2 | 1 | 2 | 2021-11-29 | Debris removal | 1 | 1 | 1 | 1 year | Open
DAE3/22A | UB | 1 | Bridge End Culvert | Rail over water | Masonry/gabions | Collapsed fencing | Worker trip over or fall | 1 | 2 | 2 | 2021-11-29 | Rebuild fencing | 1 | 2 | 2 | 1 month | Open
DAE3/23 | UB | 2 | Kielder – River Wear, Rogerley hall | Rail over water | Metallic | Open joints | Loss of strength | 2 | 1 | 2 | 2021-08-27 | Repointing | 1 | 1 | 1 | 1 year | Open | 6 | 2021-08-27 | 2027-08-26
DAE3/23 | UB | 2 | Kielder – River Wear, Rogerley hall | Rail over water | Metallic | Spalling | Loss of strength | 2 | 2 | 4 | 2021-08-27 | Recasing | 1 | 2 | 2 | 6 months | Open
DAE3/23 | UB | 2 | Kielder – River Wear, Rogerley hall | Rail over water | Metallic | Fractures | Loss of strength | 2 | 2 | 4 | 2021-08-27 | Repointing and tabbing | 1 | 2 | 2 | 6 months | Open
DAE3/23 | UB | 2 | Kielder – River Wear, Rogerley hall | Rail over water | Metallic | Undercutting of the aprons | Scour and collapse of the aprons/piers | 2 | 3 | 6 | 2021-08-27 | Rock armour or concrete bagwork | 1 | 3 | 3 | 3 months | Open
DAE3/23 | UB | 2 | Kielder – River Wear, Rogerley hall | Rail over water | Metallic | Corrosion | Loss of strength to the deck | 2 | 3 | 6 | 2021-08-27 | Clean and paint | 1 | 3 | 3 | 6 months | Open
DAE3/24 | UB | 1 | Cowburn | Rail over water | Concrete | Debris | Could get lodged and cause damage and scour in the bed | 2 | 3 | 6 | 2021-08-27 | Removal of debris | 1 | 3 | 3 | 3 months | Open | 12 | 2021-08-27 | 2033-08-24
DAE3/24 | UB | 1 | Cowburn | Rail over water | Concrete | Corrosion | Loss of strength to the deck | 2 | 2 | 4 | 2021-08-27 | Clean and paint | 1 | 2 | 2 | 6 months | Open
DAE3/25 | UB | 1 | Parson Byers Culvert | Rail over water | Masonry | Open joints | Loss of strength | 2 | 1 | 2 | 2021-08-27 | Repointing | 1 | 1 | 1 | 6 months | Open | 12 | 2021-08-27 | 2033-08-24
DAE3/25 | UB | 1 | Parson Byers Culvert | Rail over water | Masonry | Spalled, loose, and missing brickwork | Loss of strength | 2 | 2 | 4 | 2021-08-27 | Recasing | 1 | 2 | 2 | 6 months | Open
DAE3/25 | UB | 1 | Parson Byers Culvert | Rail over water | Masonry | Fractures | Loss of strength | 3 | 2 | 6 | 2021-08-27 | Repointing and tabbing | 1 | 2 | 2 | 6 months | Open
DAE3/28 | UB | 2 | Stanhope East – River | Rail over water | Metallic | Fractures | Loss of strength | 2 | 2 | 4 | 2021-08-27 | Repointing and tabbing | 1 | 2 | 2 | 6 months | Open | 6 | 2021-08-27 | 2027-08-26
DAE3/28 | UB | 2 | Stanhope East – River | Rail over water | Metallic | Spalling and missing bricks | Loss of strength | 2 | 2 | 4 | 2021-08-27 | Recasing | 1 | 2 | 2 | 6 months | Open
DAE3/28 | UB | 2 | Stanhope East – River | Rail over water | Metallic | Bulging Wingwall | Possible void is diplaced material behind, could lead to collapse | 2 | 3 | 6 | 2021-08-27 | Monitor | 2 | 3 | 6 | Ongoing | Open
DAE3/28 | UB | 2 | Stanhope East – River | Rail over water | Metallic | Corrosion | Loss of strength to the deck | 2 | 2 | 4 | 2021-08-27 | Clean and paint | 1 | 2 | 2 | 6 months | Open
DAE3/28 | UB | 2 | Stanhope East – River | Rail over water | Metallic | Buckling to the cross girder | Loss of strength to the deck | 2 | 2 | 4 | 2021-08-27 | Regularly monitor | 1 | 2 | 2 | Ongoing | Open
DAE3/28 | UB | 2 | Stanhope East – River | Rail over water | Metallic | Rotting deck timbers | Workers falling through deck | 2 | 2 | 4 | 2021-08-27 | Replace rotten timbers | 1 | 2 | 2 | 3 months | Open
DAE3/29 | OB | 1 | Stanhope Station Footbridge | Pedestrian over rail | Metallic/Timber | Missing fasteners | Loose walkway causing tripping hazard | 3 | 2 | 6 | 2021-08-27 | Replace missing fasteners | 1 | 2 | 2 | 3 months | Open | 6 | 2021-08-27 | 2027-08-26
DAE3/29 | OB | 1 | Stanhope Station Footbridge | Pedestrian over rail | Metallic/Timber | Rotten timbers | Tripping hazard | 3 | 2 | 6 | 2021-08-27 | Replace rotten timbers | 1 | 2 | 2 | 3 months | Open
DAE3/30 | UB | 3 | Stanhope West (River Wear) | Rail over water | Metallic | Loss of section/knife edging to cross girders | Loss of strength | 2 | 3 | 6 | 2021-10-14 | Monitor, repaint or apply linseed oil | 1 | 3 | 3 | Ongoing | Open | 6 | 2021-10-14 | 2027-10-13
DAE3/30 | UB | 3 | Stanhope West (River Wear) | Rail over water | Metallic | Loss of section to metallic handrails | Loss of strength to handrails, people falling | 2 | 2 | 4 | 2021-10-14 | Clean and paint, replace members if reopened | 1 | 2 | 2 | 1 year | Open
DAE3/30 | UB | 3 | Stanhope West (River Wear) | Rail over water | Metallic | Surface corrosion to XGs/MGs | Loss of strength | 1 | 2 | 2 | 2021-10-14 | Clean and paint or coat with linseed oil | 1 | 2 | 2 | 5 years | Open
DAE3/30 | UB | 3 | Stanhope West (River Wear) | Rail over water | Metallic | Deck timbers rotten or loose | People falling through deck | 3 | 3 | 9 | 2021-10-14 | Access now restricted, renew deck | 1 | 3 | 3 | 1 year | Open
DAE3/30 | UB | 3 | Stanhope West (River Wear) | Rail over water | Metallic | Missing stonework across bearing shelf, PRT1 HM | Loss of strength | 2 | 4 | 8 | 2021-10-14 | Monitor, repair if line reopens | 2 | 4 | 8 | Ongoing | Open
DAE3/30 | UB | 3 | Stanhope West (River Wear) | Rail over water | Metallic | Mortar loss and open joints | Loss of strength | 1 | 2 | 2 | 2021-10-14 | Repointing | 1 | 2 | 2 | 5 years | Open
DAE3/30 | UB | 3 | Stanhope West (River Wear) | Rail over water | Metallic | Vegetation | Loss of strength due to roots causing damage Unable to view possible defects under vegetation | 2 | 1 | 2 | 2021-10-14 | De-vegetation | 1 | 1 | 1 | 1 year | Open
DAE3/31 | UB | 1 | Flood Relief Bridge | Rail over water | Masonry | Vegetation | Loss of strength due to roots causing damage Unable to view possible defects under vegetation | 2 | 1 | 2 | 2021-10-14 | De-vegetation | 1 | 1 | 1 | 1 year | Open | 12 | 2021-10-14 | 2033-10-11
DAE3/31 | UB | 1 | Flood Relief Bridge | Rail over water | Masonry | Loss of section to metallic handrails | Loss of strength to handrails, people falling | 2 | 2 | 4 | 2021-10-14 | Clean and paint, replace members if reopened | 1 | 2 | 2 | 5 years | Open
DAE3/31 | UB | 1 | Flood Relief Bridge | Rail over water | Masonry | Mortar loss | Loss of strength | 1 | 2 | 2 | 2021-10-14 | Repointing | 1 | 2 | 2 | 5 years | Open
DAE3/33 | UB | 1 | "Bridge Over Stream" | Rail over water | Masonry | Vegetation | Loss of strength due to roots causing damage Unable to view possible defects under vegetation | 2 | 1 | 2 | 2021-10-14 | De-vegetation | 1 | 1 | 1 | 1 year | Open | 12 | 2021-10-14 | 2033-10-11
DAE3/33 | UB | 1 | "Bridge Over Stream" | Rail over water | Masonry | Cracked/eroded abutment stones | Loss of strength | 2 | 2 | 4 | 2021-10-14 | Monitor, install data tabs/Avonguards | 1 | 2 | 2 | Ongoing | Open
DAE3/33 | UB | 1 | "Bridge Over Stream" | Rail over water | Masonry | Mortar loss | Loss of strength | 2 | 2 | 4 | 2021-10-14 | Repointing | 1 | 2 | 2 | 5 Years | Open
DAE3/33 | UB | 1 | "Bridge Over Stream" | Rail over water | Masonry | Leaching/water ingress | Loss of strength | 2 | 1 | 2 | 2021-10-14 | Monitor | 1 | 1 | 1 | Ongoing | Open
DAE3/33 | UB | 1 | "Bridge Over Stream" | Rail over water | Masonry | Corrosion to handrails | Loss of strength to handrails, people falling | 2 | 2 | 4 | 2021-10-14 | Clean and paint, replace members if reopened | 1 | 2 | 2 | 5 years | Open
DAE3/34 | UB | 3 | Crag Nook | Rail over water | Metallic | Deck timbers rotten or loose | People falling through deck, inability to inspect entire structure | 3 | 3 | 9 | 2021-10-14 | Access now restricted, renew deck | 1 | 3 | 3 | 1 year | Open | 6 | 2021-10-14 | 2027-10-13
DAE3/34 | UB | 3 | Crag Nook | Rail over water | Metallic | ABT1 signs of distress/displacement | Loss of strength | 2 | 4 | 8 | 2021-10-14 | Monitor, strengthen if line reopens | 2 | 4 | 8 | Ongoing | Open
DAE3/34 | UB | 3 | Crag Nook | Rail over water | Metallic | Corrosion | Loss of strength | 1 | 2 | 2 | 2021-10-14 | Clean and paint or coat with linseed oil | 1 | 2 | 2 | 5 years | Open
DAE3/34 | UB | 3 | Crag Nook | Rail over water | Metallic | Vegetation | Loss of strength due to roots causing damage Unable to view possible defects under vegetation | 2 | 1 | 2 | 2021-10-14 | De-vegetation | 1 | 1 | 1 | 1 year | Open
DAE3/36 | UB | 2 | Rookhope Burn | Rail over water | Metallic | Rivets heavily corroded | Loss of strength | 2 | 4 | 8 | 2021-10-15 | Route not open to traffic, unlikely to cause issues without rail loading, replace if route reopens | 2 | 4 | 8 | Ongoing | Open | 6 | 2021-10-15 | 2027-10-14
DAE3/36 | UB | 2 | Rookhope Burn | Rail over water | Metallic | Vegetation | Loss of strength due to roots causing damage Unable to view possible defects under vegetation | 2 | 1 | 2 | 2021-10-15 | De-vegetation | 1 | 1 | 1 | 1 year | Open
DAE3/36 | UB | 2 | Rookhope Burn | Rail over water | Metallic | Corrosion | Loss of strength | 1 | 2 | 2 | 2021-10-15 | Clean and paint or coat with linseed oil | 1 | 2 | 2 | 5 years | Open
DAE3/36 | UB | 2 | Rookhope Burn | Rail over water | Metallic | Cracked pier stonework | Loss of strength | 2 | 1 | 2 | 2021-10-15 | Monitor | 1 | 1 | 1 | Ongoing | Open
DAE3/36 | UB | 2 | Rookhope Burn | Rail over water | Metallic | Lack of anti-trespass signage | Trespassing on the railway track, very little access in emergencies | 5 | 1 | 5 | 2021-10-19 | Install anti-trespass signage | 3 | 1 | 3 | 1 month | Open
DAE3/XX | UB | 1 | Un-named culvert (14m 0929yds) | Rail over water | Culvert (Unknown Construction) | Displacement to ground beneath track formation | Track discontinuities, loss of ballast shoulder, washout risk | 2 | 5 | 10 | 2021-10-14 | Monitor, inspect after major storms, replace structure if line reopens | 1 | 5 | 5 | Ongoing | Open | 6 | 2021-10-14 | 2027-10-13
DAE3/XX | UB | 1 | Un-named culvert (14m 0929yds) | Rail over water | Culvert (Unknown Construction) | Vegetation | Loss of strength due to roots causing damage Inspection of culvert not possible. | 2 | 1 | 2 | 2021-10-14 | De-vegetation | 1 | 1 | 1 | 1 year | Open
DAE3/XX | UB | 1 | Un-named culvert (14m 0929yds) | Rail over water | Culvert (Unknown Construction) | Condition of culvert structure unknown | Unknown defects, signs of distress clearly visible | 2 | 2 | 4 | 2021-10-14 | CCTV inspection | 1 | 2 | 2 | 1 year | Open
Formulas:
Next Exam = [Last Exam]+([Detailed Exam Regime (yrs)]*365)

## Matrix
Ref: Network Rail CRAM v1.2 received 30/11/2018
Impact area | 1 | 2 | 3 | 4 | 5
Safety/ Health/ Environment | Event with the potential for less than 20 minor injuries or a single major injury (less than .1 FWI) Minor health effects not affecting work performance or causing disability, treatment applied by First Aider onsite e.g. minor cuts & abrasions Negligible impact to a minimal area of low environmental significance, managed by internal control procedures (e.g. Spills <20 litres; Fly tipping) | Significant event with the potential of a single major injury to five major injuries (between .1 - .5 FWI) Minor health effects causing lost time injury 1-20 days with some impact on local level activities, e.g. MSK – musculoskeletal injury from manual handling with short term health issues Minor or minimal short-term impacts to the environment (e.g. Minor spill of >20 litres; dust/odour; Disturbance to locally protected Biodiversity Action Plan (BAP) species or its habitat) | Significant event with the potential of between five major injuries and two fatalities (between .5 and 2 FWI) Major health effects causing lost time injury 20+ days and/or redeployment, e.g. MSK with long term health issues, hand/arm vibration syndrome Significant impact to the wider environment, where short term (< 6 months) restoration works are needed (e.g. Confirmed spread of an invasive species; Disturbance to a statutorily protected site or a European/nationally protected species or habitat; Damage to a Site of Special Scientific Interest (SSSI); destroying the habitat of a protected species) | Catastrophic event with the potential of between two and 10 fatalities (between 2-10 FWI) Irreversible damage causing serious disability and more than 6 months off work or fatalities e.g. respirable crystalline silica (RCS) from ballast dust and asbestos from buildings to renewals Major, persistent and/or extensive impact to the environment where longer term remediation is required (> 6 months) e.g. Long term pollution involving toxic, hazardous or infectious materials/waste; Use of resources under threat of depletion; Damage to a statutorily protected site or a European / nationally protected species or habitat; Unlicensed killing of a small population of a European/ nationally protected species) | Catastrophic event with the potential of over 10 fatalities (10 FWI) Catastrophic health effects causing multiple fatalities from long term exposure in the work place e.g. silica and asbestos or effect of ill health on work e.g. sudden incapacity for a Lookout or Train Driver Catastrophic and irreversible environmental damage (e.g. Irreparable damage to protected sites and/or unlicensed killing of a local/regionally significant protected species population; Direct over- consumption of natural resources causing irreversible depletion of that resource)
Performance | Planned disruption for up to a day on any one route Project <1yr = <=1 week schedule delays Project >1yr = <=2 weeks <52hrs possession; overrun <=15mins 52hrs – week possession; overrun <=1hr 1-4week possession; overrun <= 4hrs | Unplanned disruption (for up to a day) on any one route Project <1yr = 1-2 weeks schedule delays Project >1yr = 2-4 weeks <52hrs possession; overrun 15 - 30 minute 52hrs – week possession; overrun 1-2hrs 1-4week possession; overrun 4-7hrs | Unplanned disruption (for up to a week) on any one route or Up to a day on multiple routes Project <1yr = 2-4weeks schedule delays Project >1yr = 4-8 weeks <52hrs possession; overrun 30min to 1hr 52hrs – week possession; overrun 2-4hrs 1-4week possession; overrun 7-14hrs | Unplanned disruption for over a week on multiple routes and limited access to station facilities Project <1yr = 4-6 weeks schedule delays Project >1yr = 8-12 weeks <52hrs possession; overrun 1 – 2hrs 52hrs – week possession; overrun 4-7hrs 1-4week possession; overrun 14-26hrs | All users experience prolonged and unplanned disruption to key routes. Access to major station facilities likely to be severely restricted Project <1yr = >6 weeks schedule delays Project >1yr = >12 weeks <52hrs possession; overrun >2 hrs 52hrs – week possession; overrun >7hrs 1-4week possession; overrun >26hrs
Finance | £0 - £2m OR Less than 3% of allocated budget Efficiency target 100% deliverable No Breach of cash limits | £2 - 10m OR between 3% - 5% of allocated budget Efficiency target >90% deliverable Minor breach of cash limits | £10 - 50m OR between 5% and 7% of allocated budget Efficiency target 80-90% deliverable Minor to moderate breach of cash limits to create minimum value | £50 - 250m OR between 7% and 10% of allocated budget Efficiency target 60-80% deliverable Moderate breach of cash limits where there is potential to create some value | Over £250m OR Greater than 10% of allocated budget Efficiency target <60% deliverable Significant breach of cash limit or where there is the potential to create significant value
Asset Management | Does not directly and adversely affect either railway infrastructure reliability or railway infrastructure condition Or Direct and adverse impact on railway infrastructure reliability or railway infrastructure condition is minimal Failure to achieve annual CRI target Failure to achieve annual contribution to the CSI target | Directly and adversely affects railway infrastructure reliability within the current performance year Or Directly and adversely affects railway infrastructure condition within the current control period Failure to deliver 50% CRI target value in year concerned Failure to achieve annual contribution by such a margin as this threatens CSI outturn for CP5 | Directly and adversely affects railway infrastructure reliability over the current and next performance year Or Directly and adversely affects railway infrastructure condition over the current & next control period Failure to improve CRI target value in Control Period (or 5 yr period) Failure to achieve CSI in CP5 | Directly and adversely affects railway infrastructure reliability over the next 3-4 performance years Or Directly and adversely affects railway infrastructure condition over the next three control periods (11+ years) Deterioration in CRI between 10% to 49% in Control Period (or 5 yr period) – (against target) Failure by up to 0.5% to deliver CSI in CP5 | Directly and adversely affects railway infrastructure reliability over the next 5+ performance years Or Directly and adversely affects railway infrastructure condition over the next four control periods (16+ years) Deterioration in CRI by > 50% in Control Period (or 5 yr period) - (against target) A major shortfall in CSI by >0.5% in CP5
Satisfaction & Reputation | Short-term adverse local stakeholder reaction Short term loss of morale with poor performance of non-critical activities Minor legal issues, non-compliance or breach of regulation. Legal challenge, minor out of court settlement limited to parties involved and expected outcome known No ORR action. | Adverse local media reports over a period. Localised stakeholder concern. Minor disengagement. Effectiveness / Efficiency compromised with service failures in non-critical activities Breach of regulation with investigation or report to authority with prosecution and/or moderate fine possible. Limited to parties involved but outcome uncertain Risk scores a 1 – 2 on the ORR regulatory escalator | Significant local and / or regional reports including social media. National media interest creating public concern. Negative national stakeholder statements from both government departments and/or TOC/FOCs. Some disengagement leading to effectiveness / efficiency compromised in some critical activities. Serious breach of regulation. Major litigation/ Class action/ criminal prosecution/prohibition notice. Local profile and outcomes uncertain. Risk scores a 3 on the ORR regulatory escalator | Extensive prolonged diverse national reporting and public disputes with key stakeholders, e.g. breakdown of a TOC alliance. A major downturn in company-wide engagement leading to service failures within some critical activities. Significant prosecution and fines. Very serious litigation including class actions. National profile, impact on current/future business operations. Risk scores a 4 on the ORR regulatory escalator | Extensive and prolonged negative reporting nationally or public disputes with key stakeholders, including political and/or TOC/FOCs. Escalation to external bodies inevitable & impossible to contain in medium term. Potential for significant changes imposed on NR, its responsibilities and structure A significant downturn in companywide engagement. Serious failings across most services National profile, major impact on current and future business operation. Prosecution likely. Potential prison terms for executives and/or high fines for organisation. Multiple litigations. Risk scores 5 on the ORR regulatory escalator
Liklihood | 1 | 2 | 3 | 4 | 5
Criteria | <5% Very Low likelihood the risk will occur Risk would occur less than once in 25 years | 5 – 20% Low likelihood the risk will occur Risk would occur between once in 25 years or up to once in 5 years | 21 – 50% Medium likelihood the risk will occur Risk would occur between once in 5 years to just less than once a year | 51 – 75% High likelihood the risk will occur Risk would occur between 1 and 5 times a year | >75% Very High likelihood the risk will occur Risk would occur 5 times a year or more
Severity
[8 empty] | 1 | 2 | 3 | 4 | 5
[6 empty] | Liklihood | 1 | 1 | 2 | 3 | 4 | 5 | Acceptable | 1 - 8
[7 empty] | 2 | 2 | 4 | 6 | 8 | 10 | Consider reasonably practicable improvements | 9 - 11
[7 empty] | 3 | 3 | 6 | 9 | 12 | 15 | Consider practical improvements | 12 -14
[7 empty] | 4 | 4 | 8 | 12 | 16 | 20 | Unacceptable | 15 - 19
[7 empty] | 5 | 5 | 10 | 15 | 20 | 25 | Intolerable | 20 - 25

## Frequency
Inspection Frequency
Primary material type of Bridge | Interval Years
| Lower | Standard | Higher
Aluminium | 12 | 6 | 3
Brick arch | 18 | 12 | 6
Cast iron structural elements that carry rail and/or road traffic loads and which are subject to tensile stress | 3 | 3 | 3
Cast iron structural elements that are not subject to tensile stress | 6 | 6 | 3
Cast in situ reinforced concrete | 12 | 6 | 6
Early steel (pre-1956) | 6 | 6 | 3
Fibre-reinforced polymer (FRP) | 12 | 6 | 3
Mass concrete | 18 | 12 | 6
Post-tensioned concrete | 6 | 3 | 1
Pre-cast concrete | 12 | 6 | 6
Pre-tensioned concrete | 12 | 6 | 6
Steel | 12 | 6 | 3
Stone | 12 | 6 | 6
Timber | 3 | 2 | 1
Weathering Steel | 12 | 6 | 3
Wrought iron | 6 | 6 | 3