## Structures
name | lat | lng | ELR | From | To | Track | Features /Identification/Local Name |  | Asset Type | Hazard Ref. | Description of Scenario | Description of Identified Hazard | Description of Consequence | Consequence Category | Persons at Risk | Current Risk Reduction Measures | Current Risk |  |  |  | CSM-RA Principle |  |  |  | Proposed Alternative Risk Reduction Measures | Target Risk |  |  |  | Evidence | Status (Open/Closed) | Risk Reduction Action Plan |  | Residual Hazard Description | Residual Hazard Control Measures | Residual Hazard Owner | Project Transfer Status | Work Arising Estimate | Actual Date | OS Reference
|  |  |  | Miles | Miles | [11 empty] | Liklihood | Severity | Rating | Date Logged | Qualitative / Quantitative result or N/A | Applicable risk criteria | Evidence (e.g. NR Standard (including sub-clause) | Treat (Reduce)/ Tolerate (Accept)/ Transfer (Share or Transfer)/ Terminate (Avoid) |  | Liklihood | Severity | Rating | Target Date |  |  | Action Plan Owner | Due Date
|  |  | GSM4 | 106.0572 | 106.0572 | Up & Down | 63 | WAITE'S BRIDGE | Overbridge | BCL/CIV/0001 | Outside of our scope | Structure inspected by NR, not BCL. | Any defects could affect RIDC operation if not properly communicated | Asset Management | All | Track patrol | 2 | 3 | 5 | 2018-04-12 |  |  |  |  | Request inspection reports from NR or obtain via other methods | 1 | 1 | 2 | 2018-10-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 106.1452 | 106.1452 | Up & Down | 61 | RBE_ASFORDBY ROAD | Overbridge | BCL/CIV/0002 | Outside of our scope | Structure inspected by NR, not BCL. | Any defects could affect RIDC operation if not properly communicated | Asset Management | All | Track patrol | 2 | 3 | 5 | 2018-04-12 |  |  |  |  | Request inspection reports from NR or obtain via other methods | 1 | 1 | 2 | 2018-10-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 106.1666 | 107.0309 | Up & Down | 60 | Asfordby Tunnel | Tunnel Bore | BCL/CIV/0003 | Outside of our scope | Structure inspected by NR, not BCL. | Any defects could affect RIDC operation if not properly communicated | Asset Management | All | Track patrol | 2 | 3 | 5 | 2018-04-12 |  |  |  |  | Request inspection reports from NR or obtain via other methods | 1 | 1 | 2 | 2018-10-01 |  | Closed | D Gent | 2019-04-01
60 | 52.7674 | -0.9358 | GSM4 | 106.1666 |  | Both | 60 | Asfordby Tunnel | Tunnel | BCL/CIV/0233 | Structural defect | Severely damaged brickwork to the portal flume, risk of dropping brickwork | Train or personnel struck, structural failure | Asset Management | All | Track patrol and annual visual inspection | 2 | 2 | 4 | 2018-09-03 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Repair Severely damaged brickwork to the portal flume, risk of dropping brickwork | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 106.1672 | ? | DRL | Flume (Downside) at Asfordby Tunnel Sth Portal |  | Culvert | BCL/CIV/0004 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 exam completed | 1 | 1 | 2 |  |  | Closed | D Gent | 2019-04-01
|  |  | GSM5 | 107.0374 | 107.04 | U&D Asfordby | Concrete Battered Revetment Asfordby Tunnel Nth (Upside) (Approx length 1ch) |  | Culvert | BCL/CIV/0005 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 Exam completed, no significant defects recorded | 1 | 1 | 2 |  |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 107.044 | 107.044 | Up & Down | RIDC BOUNDARY WITH NR MAIN LINE |  | Pway | BCL/CIV/0006
|  |  | GSM4 | 107.087 | 107.087 | Up & Down |  | Asfordby | UTX | BCL/CIV/0007 | Uninspected structure | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Structure failure | Safety | Passengers & Workforce | Track patrol | 2 | 3 | 5 | 2018-04-27 |  |  |  |  | Undertake viusual inspection | 1 | 1 | 2 | 2018-10-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 107.09 | ? | DRL | Large retaining Wall, (Brick) high up cutting slope nr Asfordby Nth Jn (Upside) Approx length 3ch |  | Culvert | BCL/CIV/0008 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 exam completed | 1 | 1 | 2 |  |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 107.0902 | 107.0902 | Up & Down | 59 | Arched Culvert | Culvert | BCL/CIV/0161 | Missing safety fence | Safety defect | Falls from height | Safety | Workforce | Track patrol | 2 | 5 | 7 | 2018-08-01 |  |  |  |  | Visually inspect structure and replace missing fence if required | 1 | 1 | 2 | 2018-09-01 |  | Closed | D Gent | 2018-10-01
59 | 52.7674 | -0.9358 | GSM4 | 107.0902 |  | Both | 59 | Underbridge | Underbridge | BCL/CIV/0234 | Structural defect | New Safety fence required | Injury to personnel | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Provide New Safety fence required | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Injury to personnel | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 107.0902 | 107.0902 | Up & Down | 59 | Arched bridge( Assumed 1.8m diameter) | Underbridge | BCL/CIV/0009 | Outside of our scope | Structure inspected by NR, not BCL. | Any defects could affect RIDC operation if not properly communicated | Asset Management | All | Track patrol | 2 | 3 | 5 | 2018-04-27 |  |  |  |  | Request inspection reports from NR or obtain via other methods | 1 | 1 | 2 | 2018-10-01 | BCL/CIV/0234 | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 107.0924 | 107.0924 | Up & Down |  | Pipe | Pipe | BCL/CIV/0010 | Unknown structure | No records made available | May be unknown hazards | Asset Management | Workforce | Track patrol | 2 | 2 | 4 | 2018-04-26 |  |  |  |  | Undertake viusual inspection | 1 | 1 | 2 | 2018-10-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 107.0924 |  |  | 58 | Welby Road | Underbridge | BCL/CIV/0235 | Structural defect | Provide bridge strike plates (one has Incorrect telephone number and the other vandalised) | Bridge strikes go unreported | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Provide bridge strike plates (one has Incorrect telephone number and the other vandalised) - strrike plates replaced on 8/2/19 | 1 | 1 | 2 | 2019-04-01 |  | Closed | Network Rail | 2019-04-01 | Bridge strikes go unreported | Track patrol and annual visual inspection | Network Rail |  |  | 2019-02-08
|  |  | GSM4 | 107.0924 | 107.0924 | Up & Down | 58 | Welby Road UB | Underbridge | BCL/CIV/0011 | Structural defect | Missing bridge strike plates | bridge struck and not reported | Asset Management | Members of public (MoP) | Annual vissual inspection req | 3 | 1 | 4 | 2018-04-26 |  |  |  |  | Next Detailed - 2021 Provide bridge strike plates (one has Incorrect telephone number and the other vandalised) | 1 | 1 | 2 | 2018-06-01 | BCL/CIV/0235 | Closed | D Gent | 2018-06-01
|  |  | GSM4 | 107.1 | ? | DRL | Sheet piles retaining wall Asfordby North, Nr Br 58 |  | Retaining Wall | BCL/CIV/0012 |  | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | deterioration of structure | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-13 |  |  |  |  | Visual inspection req exam completed | 1 | 1 | 2 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 107.1232 | 107.1232 |  | 57A BRICK CULVERT |  | Culvert | BCL/CIV/0013 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 Exam completed, no significant defects recorded | 1 | 1 | 2 |  | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM5 | 107.1325 | 107.1325 |  | Asfordby Depot |  | Building | BCL/CIV/0014 | No inspection report | there is no inspection report so we currently have no idea of the strcutural consdition |  | Safety | All |  | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | Serco maintenance liability | 1 | 1 | 2 | 2019-04-01 | Not BCL responsibility | Closed | D Gent | Not set
|  |  | GSM4 | 107.1408 | 107.1408 |  |  | Retaining Wall | Retaining Wall | BCL/CIV/0015 |  | Retaining Wall required a complete De-vegetation so that a Detailed exam can be carried out in 14/15 |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Retaining Wall required a complete De-vegetation so that a Detailed exam can be carried out in 14/15 | 1 | 1 | 2 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 107.145 | 107.158 |  | GSM4 107/A1 Retaining Wall |  | Retaining Wall | BCL/CIV/0160 | Structure not examined | Heavy vegetation obscuring structure | Structure could be in a state of dis-repair / failure | Asset Management | Passengers | Track patrol | 1 | 3 | 4 | 2018-07-02 |  |  |  |  | De-vegetate the locxation and complete the examination of the structure | 1 | 1 | 2 | 2019-02-01 |  | Closed | D Gent | 2019-02-01
|  |  | GSM5 | 107.1477 | 107.1477 |  | STATIC FIXED POSITION CRANE |  | Structure | BCL/CIV/0016 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | Not fixed
57 | 52.7702 | -0.94611 | GSM4 | 107.1716 |  |  | 57 | Houghton's Bridge | Underbridge | BCL/CIV/0200 | Structural defect | Reinstate broken Date-Tabs 2no on downside high mileage wingwall and 2no on downside buttresses | Unable to track bridge deterioration | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Re-point locally and reinstate broken Date-Tabs 2no on downside high mileage wingwall and 2no on downside buttresses | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Unable to track bridge deterioration | Track patrol and annual visual inspection | Network Rail
57 | 52.7702 | -0.94611 | GSM4 | 107.1716 |  | Both | 57 | Houghton's Bridge | Underbridge | BCL/CIV/0245 | Bridge failure due to excessive vehicle loading | Bridge has been assessed as being RA10, but there is currently no vehicle restrictions and the line speed is 115mph in this section | Bridge deforms under loading leading to failure | Asset Management | All | Annual vissual inspection req | 2 | 3 | 5 | 2018-09-26 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Short term: axle weight of actuial traffic is 11tonnes Medium term: Carry out a more detailed assessment (previous was done using the L0 tool); | 1 | 1 | 2 | 2018-11-01 |  | Open | D Gent | 2018-12-01 | Bridge failure after prolongued deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 107.1716 | 107.1716 | Up & Down | 57 | Houghton's Bridge UB | Underbridge | BCL/CIV/0017 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | BCL/CIV/0200 | Closed | D Gent | Not fixed
|  |  | GSM4 | 107.924 | 107.924 | Up & Down | 58A | Pipe | Pipe | BCL/CIV/0018 | Unknown structure | No records made available | May be unknown hazards | Asset Management | Workforce | Track patrol | 2 | 2 | 4 | 2018-04-26 |  |  |  |  | Undertake viusual inspection examination complete | 1 | 1 | 2 | 2018-10-01 | Annual report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 108 | 108 |  | 56A BRICK CULVERT |  | Culvert | BCL/CIV/0019 | Missing bricks | Structual defect | Deterioration of structure | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-26 |  |  |  |  | Re-case missing brickwork | 1 | 1 | 2 |  | BCL/CIV/0202 | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 108 | 108 | Up & Down | UB57 |  | UTX | BCL/CIV/0020 | Unrecorded structure defects | Structures Defect | Unknown defects could affect line operation | Asset Management | All | Track patrol | 2 | 2 | 4 | 2018-04-27 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
56A | 52.7702 | -0.94611 | GSM4 | 108 |  |  | 56A | Culvert | Culvert | BCL/CIV/0202 | Structural defect | Reacase missing brickwork | Structural failure | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 |  |  |  | Tolerate | Reacase missing brickwork - if diameter too small, will have to consider lining or re-building the structure | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Structural failure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 108.022 | 108.022 | Up & Down | 56 | Gravel Hole Bridge OB | Overbridge | BCL/CIV/0021 | Vegetation & Fractures | Vegetation and structural defect | Deterioration of structure |  |  | Annual vissual inspection req | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Next Detailed - 2020 1) remove vegetation from H/M upside. 2)Point up fractures and date tab at various locations (behind face riungs, span 3, etc.) | 1 | 1 | 2 | 2019-04-01 | BCL/CIV/0246 | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 108.0484 | 108.0484 |  | 55B BRICK CULVERT |  | Culvert | BCL/CIV/0022 | Missing safety fence | Safety defect | Falls from height | Safety | Workforce | Track patrol | 2 | 5 | 7 | 2018-04-26 |  |  |  |  | Visually inspect structure and replace missing fence if required | 1 | 1 | 2 | 2018-09-01 |  | Closed | D Gent | 2018-10-01
55B | 52.7721 | -0.952 | GSM4 | 108.0484 | 108.0484 | Both | 55B BRICK CULVERT |  | Culvert | BCL/CIV/0162 | Safety defect | Collapsed culvert | Failure of structure resulting in failure of track | Safety/ Health/ Environment | All | Track patrol | 3 | 2 | 5 | 2018-08-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Repair collapsed section of culvert | 1 | 1 | 2 | 2019-04-01 |  | Open | D Gent | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
55B | 52.7721 | -0.952 | GSM4 | 108.0484 |  | Both | 55B | Culvert | Culvert | BCL/CIV/0236 | Structural defect | Collapsed culvert | Injury to personnel | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Rebuild collapsed section and povide safety fence to headwalls | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Injury to personnel | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 108.077 | 108.077 |  | 55A BRICK CULVERT |  | Culvert | BCL/CIV/0023 | Missing safety fence | Safety defect | Falls from height | Safety | Workforce | Track patrol | 2 | 5 | 7 | 2018-04-26 |  |  |  |  | Visually inspect structure and replace missing fence if required | 1 | 1 | 2 | 2018-09-01 |  | Closed | D Gent | 2018-10-01
55A | 52.7739 | -0.95492 | GSM4 | 108.077 |  | Both | 55A | Culvert | Culvert | BCL/CIV/0237 | Structural defect | Provide safety fence to headwalls | Injury to personnel | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Provide safety fence to headwalls | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Injury to personnel | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 108.0813 | 108.0813 |  | 1080813 3FT 6INS CULVERT SOLD |  | Culvert | BCL/CIV/0024 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 Exam completed, no significant defects recorded | 1 | 1 | 2 |  |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 108.0814 | 108.0814 | Up & Down | 55 | Morris' Bridge OB | Overbridge | BCL/CIV/0025 | [5 empty] | Annual vissual inspection req | 3 | 1 | 4 | 2018-04-26 |  |  |  |  | Next Detailed - 2019 1) Vegetation requires removal on upside parapet, H/M end | 1 | 1 | 2 | 2019-04-01 | BCL/CIV/0238 | Closed | D Gent | 2019-04-01
55 | 52.7748 | -0.95489 | GSM4 | 108.0814 |  |  | 55 | Morris's Bridge | Overbridge | BCL/CIV/0238 | Structural defect | repair displaced bricks on HM Parapet at centre under coping. | Train or personnel struck, structural failure | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | repair displaced bricks on HM Parapet at centre under coping. | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
54 | 52.7748 | -0.95638 | GSM4 | 108.088 |  |  | 54 | Saxelby Tunnel | Tunnel | BCL/CIV/0201 | Structural defect | 1) Edwalton portal. Brickwork, loose bricks and open joints to an area of 1 m2. Recommend replace brickwork priority 3. 2) Melton portal. Brickwork, loose and missing bricks and open joints to an area of 4 m2. Recommend replace brickwork priority 3. | Train or personnel struck, structural failure | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) Edwalton portal. Brickwork, loose bricks and open joints to an area of 1 m2. Recommend replace brickwork priority 3. 2) Melton portal. Brickwork, loose and missing bricks and open joints to an area of 4 m2. Recommend replace brickwork priority 3. | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
108/A1 | 52.7748 | -0.95638 | GSM4 | 108.0924 | 108.0924 |  | 108/A1 | Retaining Wall | Retaining Wall | BCL/CIV/0026 |  | Retaining Wall not located at time of exam More details required |  | Asset Management | Workforce | Track patrol | 2 | 2 | 4 | 2018-04-26 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Retaining Wall not located at time of exam More details required | 1 | 1 | 2 | 2019-04-01 |  | Open | D Gent | 2018-08-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 108.0967 | 108.1496 | Up & Down | GSM4/54T - Saxelbye Tunnel |  | Tunnel Bore | BCL/CIV/0159 | Asbetos identified | Asbestos | Asbestos-related health injuries | Safety | Workforce Health & Safety | Identified and isolated | 1 | 5 | 6 | 2018-05-21 |  |  |  |  | It is clearly difficult to remove this asbestos so the best solution currently is to isolate and leave it alone Identify exact location during visual examination Implement the use of breathing apperatus. | 1 | 5 | 6 | 2018-09-01 |  | Closed | D Gent | 2019-04-01 | Asbestos | Isolate and leave alone | NR
|  |  | GSM4 | 108.0976 | 108.1517 |  | Radio mast |  | Radio Mast | BCL/CIV/0027 | Unrecorded structure defects | Radio Mast, no records available, visual inspection required 2018 | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 1 | 4 | 2018-04-12 |  |  |  |  | Visual inspection required 2018 | 1 | 2 | 3 | 2018-11-01 |  | Closed | D Gent | 2018-12-01
|  |  | GSM4 | 108.0976 | 108.1517 | Up & Down | 54 | Saxelby tunnel | Tunnel Bore | BCL/CIV/0028 | Structural Defect+I1081:AD1081 | Defects from previous detailed exam | Further deterioration of structure | Asset Management | Passengers & Workforce | Annual vissual inspection req | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Next Detailed - 2019 Colin Watson Comment:1) Edwalton portal. Brickwork, loose bricks and open joints to an area of 1 m2. Recommend replace brickwork priority 3. (Proposal taken from visual examination of 10/05/12. Visual of 16/08/13 and this visual show no deterioration.) 2) Melton portal. Brickwork, loose and missing bricks and open joints to an area of 4 m2. Recommend replace brickwork priority 3. (Proposal taken from visual examination of 10/05/12. Visual of 16/08/13 and this visual show no deterioration.) | 1 | 1 | 2 | 2019-04-01 | Ref: BCL/CIV/0201 | Closed | D Gent
|  |  | GSM4 | 108.1254 | 108.1254 | Up & Down | Saxelbye Tunnel Shaft 1 (Open) |  | Tunnel Shaft | BCL/CIV/0029 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | Not fixed
56 | 52.7711 | -0.94905 | GSM4 | 108.22 |  | Both | 56 | Gravel Hole Bridge | Overbridge | BCL/CIV/0246 | Structural defect in barrel of Span 2 | 1) Pin and grout fractures to soffit; 2) Remove coping stones, dismantle area of loose brickwork and re-build; 3) Consider technical monitoring of parapet to determine if any further movement. | Train or personnel struck, structural failure | Safety/ Health/ Environment | All | Track patrol and annual visual inspection | 2 | 2 | 4 | 2018-12-14 | Qualitative | Explicit Risk Estimation | This defect has been risk scored in accordance with the NR CRAM as instructed by C Browne on 14/12/18. D Gent believes it requires more urgent attention | Tolerate | Monitoring by weekly track patrol until 01/02/2019, then daily monitoring by track patrol team throughout February and March (the anticipated periods of sustained freezing wetaher). Weatehr and temperature will be monitored and monitoring regime altared accordingly. Remedial works planned for early 2019 | 2 | 2 | 4 | 2018-12-14 |  | Open | Network Rail | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
56 | 52.7711 | -0.94905 | GSM4 | 108.22 |  | Both | 56 | Gravel Hole Bridge | Overbridge | BCL/CIV/0249 | Structural defect in barrel of Span 2 | 1) fractures to soffit; 2) Loose coping stone 3) Loose brickwork in soffit | Train or personnel struck, structural failure | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-12-14 | Qualitative | Explicit Risk Estimation | This defect has been risk scored in accordance with the NR CRAM as instructed by C Browne on 14/12/18. D Gent believes it requires more urgent attention | Tolerate | Monitoring by weekly track patrol until 01/02/2019, then daily monitoring by track patrol team throughout February and March (the anticipated periods of sustained freezing wetaher). Weatehr and temperature will be monitored and monitoring regime altared accordingly. Remedial works planned for early 2019 | 2 | 3 | 5 | 2018-12-14 |  | Open | Network Rail | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 108.22 |  | Both | 56 | Gravel Hole Bridge | Overbridge | BCL/CIV/0252 | Structural defect in barrel of Span 2 | 1) Pin and grout fractures to soffit; 2) Remove coping stones, dismantle area of loose brickwork and re-build; 3) Consider technical monitoring of parapet to determine if any further movement. | Train or personnel struck, structural failure | Satisfaction & Reputation | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-12-14 | Qualitative | Explicit Risk Estimation | This defect has been risk scored in accordance with the NR CRAM as instructed by C Browne on 14/12/18. D Gent believes it requires more urgent attention | Tolerate | Monitoring by weekly track patrol until 01/02/2019, then daily monitoring by track patrol team throughout February and March (the anticipated periods of sustained freezing wetaher). Weatehr and temperature will be monitored and monitoring regime altared accordingly. Remedial works planned for early 2019 | 2 | 3 | 5 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
56 | 52.7711 | -0.94905 | GSM4 | 108.22 |  | Both | 56 | Gravel Hole Bridge | Overbridge | BCL/CIV/0253 | Structural defect in barrel of Span 2 | 1) Pin and grout fractures to soffit; 2) Remove coping stones, dismantle area of loose brickwork and re-build; 3) Consider technical monitoring of parapet to determine if any further movement. | Train or personnel struck, structural failure | Performance | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-12-14 | Qualitative | Explicit Risk Estimation | This defect has been risk scored in accordance with the NR CRAM as instructed by C Browne on 14/12/18. D Gent believes it requires more urgent attention | Tolerate | Monitoring by weekly track patrol until 01/02/2019, then daily monitoring by track patrol team throughout February and March (the anticipated periods of sustained freezing wetaher). Weatehr and temperature will be monitored and monitoring regime altared accordingly. Remedial works planned for early 2019 | 1 | 3 | 4 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
56 | 52.7711 | -0.94905 | GSM4 | 108.22 |  | Both | 56 | Gravel Hole Bridge | Overbridge | BCL/CIV/0250 | Risk of heavy machinary impacting with weakened masonry parapets | 1) Pin and grout fractures to soffit; 2) Remove coping stones, dismantle area of loose brickwork and re-build; 3) Consider technical monitoring of parapet to determine if any further movement. | Train or personnel struck, structural failure | Safety/ Health/ Environment | All | Track patrol and annual visual inspection | 2 | 2 | 4 | 2018-12-14 | Qualitative | Explicit Risk Estimation | This defect has been risk scored in accordance with the NR CRAM as instructed by C Browne on 14/12/18. D Gent believes it requires more urgent attention | Tolerate | Bridge users should be briefed on structural issues and asked to be careful when crossing. | 1 | 2 | 3 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
56 | 52.7711 | -0.94905 | GSM4 | 108.22 |  | Both | 56 | Gravel Hole Bridge | Overbridge | BCL/CIV/0251 | Risk of heavy machinary impacting with weakened masonry parapets | 1) Pin and grout fractures to soffit; 2) Remove coping stones, dismantle area of loose brickwork and re-build; 3) Consider technical monitoring of parapet to determine if any further movement. | Train or personnel struck, structural failure | Asset Management | All | Track patrol and annual visual inspection | 2 | 2 | 4 | 2018-12-14 | Qualitative | Explicit Risk Estimation | This defect has been risk scored in accordance with the NR CRAM as instructed by C Browne on 14/12/18. D Gent believes it requires more urgent attention | Tolerate | Bridge users should be briefed on structural issues and asked to be careful when crossing. | 1 | 2 | 3 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 109 | 109 | Up & Down | 53 | Saxelby to Asfordby Road UB | Underbridge | BCL/CIV/0030 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol 23/07/18 - Visual exam undertaken by NR and report submitted | 3 | 2 | 5 | 2018-04-30 |  |  | NR Visual Exam report |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | Not fixed
|  |  | GSM4 | 109.0264 |  |  | 52 | Saxelby Road | Underbridge | BCL/CIV/0203 | Structural defect | Consider repointing repairs to open joints to wing walls | Structural failure | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 |  |  |  |  | Consider repointing repairs to open joints to wing walls
|  |  | GSM4 | 109.0264 | 109.0264 | Up & Down | 52 | Saxelby Road Bridge UB | Underbridge | BCL/CIV/0031 | Unrecorded structure defects | Cast iron underbridge, pay extra attention | Structure failure | Safety | Passengers & Workforce | Track patrol | 2 | 3 | 5 | 2018-04-27 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 109.0264 | 109.0264 | Up & Down | 52 | Saxelby Road Bridge UB | Underbridge | BCL/CIV/0032 | Detailed Exam Required | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Missing bridge strike plates |  |  | Track patrol | 1 | 3 | 4 | 2018-04-11 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 109.033 | ? | DRL | Saxelby old station Platform Wall Upside (Approx length 5ch) |  | Culvert | BCL/CIV/0033 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 |  |  | 0 |  |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 109.066 | 109.066 |  | 51B BRICK CULVERT |  | Culvert | BCL/CIV/0034 | Deterioration of structure | vegetation and structural defect | Further deterioration of structure | Safety | Workforce | Track patrol | 2 | 3 | 5 | 2018-04-12 |  |  |  |  | Both head walls need to under go some de-vegetation works, and re-pointing and date tabing the fracture at one end | 1 | 1 | 2 |  | BCL/CIV/0204 | Closed | D Gent | 2019-04-01
51B | 52.7839 | -0.97099 | GSM4 | 109.066 |  |  | 51B | Culvert | Culvert | BCL/CIV/0204 | Structural defect | Re-pointing and date tabing the fracture at one end | Unable to track bridge deterioration | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Re-pointing and date tabing the fracture at one end | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Unable to track bridge deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 109.0836 | 109.0836 |  | 108/A1 | Retaining Wall | Retaining Wall | BCL/CIV/0035 |  | No records |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 | [5 empty] | 1 | 1 | 2 | 2018-08-01 | Ref: BCL/CIV/0026 | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 109.1276 | 109.1276 | Up & Down | 51A | Pipe | Pipe | BCL/CIV/0036 | Unknown structure | No records made available | May be unknown hazards | Asset Management | Workforce | Track patrol | 2 | 2 | 4 | 2018-04-26 |  |  |  |  | Consider a detailed examination to determine condition under track which will require the syphon being pumped out, flows stanked off and CCTV | 1 | 1 | 2 | 2018-10-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 109.1385 | 109.1385 |  | 1091385 4'X 3' OPEN BRICK CULVERT RUNS TO 110M |  | Culvert | BCL/CIV/0037 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 Exam completed, no significant defects recorded | 1 | 1 | 2 |  |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 109.1386 | 109.1386 |  |  | Side of line bridge | Side of line Bridge | BCL/CIV/0038 |  | No records |  | Asset Management | Workforce | Track patrol | 2 | 2 | 4 | 2018-04-26 | [5 empty] | 1 | 1 | 2 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 109.1751 | 109.1751 | DRL | Flume (Downside) at end of Open drainage Channel |  | Culvert | BCL/CIV/0039 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 exam completed | 1 | 1 | 2 |  |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 110.0027 | 110.0127 | Up & Down | Grimston Covered Way |  | Overbridge | BCL/CIV/0040 | [5 empty] | Annual vissual inspection req | 3 | 1 | 4 | 2018-04-11 |  |  |  |  | Next Detailed - 2021 | 1 | 1 | 2 | 2018-10-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 110.0027 | 110.0127 | Up & Down | Grimston Covered Way |  | Tunnel Bore | BCL/CIV/0041 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | Not fixed
|  |  | GSM4 | 110.0044 | 110.0132 | Up & Down | 50 | Saxelbye Covered Way | Overbridge | BCL/CIV/0042 | Structures Defect | Structures Defect | Unknown defects could affect line operation | Asset Management |  | Annual vissual inspection req | 2 | 2 | 4 | 2018-04-27 |  |  |  |  | Carry out visual inspection exam completed | 1 | 1 | 2 | 2018-10-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 110.0044 | 110.0132 | Up & Down | 50 | Saxelbye Covered Way | Overbridge | BCL/CIV/0043 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure Exam completed, no significant defects identified | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | Not fixed
|  |  | GSM4 | 110.0307 | 110.1562 | Up & Down | GSM4/49T - Grimston Tunnel |  | Tunnel Bore | BCL/CIV/0158 | Asbetos identified | Asbestos | Asbestos-related health injuries | Safety | Workforce Health & Safety | Identified and isolated | 1 | 5 | 6 | 2018-05-21 |  |  |  |  | It is clearly difficult to remove this asbestos so the best solution currently is to isolate and leave it alone Identify exact location during visual examination Implement the use of breathing apperatus. | 1 | 5 | 6 | 2018-09-01 |  | closed | D Gent | 2019-04-01 | Asbestos | Isolate and leave alone | NR
|  |  | GSM4 | 110.05 | 110.05 | Up & Down | 49 | Grimston Tunnel Shaft 1 (Open) | Tunnel Shaft | BCL/CIV/0044 | Detailed Exam required 2018 inc shafts | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Unknown defects could affect line operation | Asset Management | All | Track patrol | 2 | 3 | 5 | 2018-04-27 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 | Ref: BCL/CIV/0239 | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 110.071 | 110.071 | Up & Down | 49 | Grimston Tunnel Shaft 2 (Open) | Tunnel Shaft | BCL/CIV/0045 | Detailed Exam required 2018 inc shafts | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Structure failure | Safety | Passengers & Workforce | Track patrol | 2 | 3 | 5 | 2018-04-27 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 | Ref: BCL/CIV/0239 | Closed | D Gent | 2018-08-01
49 | 52.7939 | -0.97965 | GSM4 | 110.088 |  | Both | 49 | Grimston Tunnel | Tunnel | BCL/CIV/0239 | Structural defect | 1) Shaft 2. Ring dam is leaking. Recommend clear ring dams and down pipes of debris and repair as required. Priority 2. 2) Melton Portal, parapet. Loose and missing brickwork in areas to front and back of portal parapet. Recommend that brickwork is replaced. 4) Melton Portal, wing wall. Loose brickwork to top of wing wall area 3 m2. Recommend that top courses are taken down, vegetation removed and brickwork rebuilt 5) Melton Portal, wing wall. Loose brickwork to top of wing wall area 3 m2. Recommend that top courses are taken down, vegetation removed and brickwork rebuilt. | Structural failure after prolonged deterioration | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) Shaft 2. Ring dam is leaking. Recommend clear ring dams and down pipes of debris and repair as required. Priority 2. 2) Melton Portal, parapet. Loose and missing brickwork in areas to front and back of portal parapet. Recommend that brickwork is replaced. 4) Melton Portal, wing wall. Loose brickwork to top of wing wall area 3 m2. Recommend that top courses are taken down, vegetation removed and brickwork rebuilt 5) Melton Portal, wing wall. Loose brickwork to top of wing wall area 3 m2. Recommend that top courses are taken down, vegetation removed and brickwork rebuilt. | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Structural failure after prolonged deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 110.093 | 110.093 | Up & Down | 49 | Grimston Tunnel Shaft 3 (Open) | Tunnel Shaft | BCL/CIV/0046 | Detailed Exam required 2018 inc shafts | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Structure failure | Safety | Passengers & Workforce | Track patrol | 2 | 3 | 5 | 2018-04-27 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 | Ref: BCL/CIV/0239 | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 110.1181 | 110.1181 | Up & Down | 49 | Grimston Tunnel Shaft 4 (Open) | Tunnel Shaft | BCL/CIV/0047 | Detailed Exam required 2018 inc shafts | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Structure failure | Safety | Passengers & Workforce | Track patrol | 2 | 3 | 5 | 2018-04-27 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 | Ref: BCL/CIV/0239 | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 110.1387 | 110.1387 | Up & Down | 49 | Grimston Tunnel Shaft 5 (Open) | Tunnel Shaft | BCL/CIV/0048 | Detailed Exam required 2018 inc shafts | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Structure failure | Safety | Passengers & Workforce | Track patrol | 2 | 3 | 5 | 2018-04-27 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 | Ref: BCL/CIV/0239 | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 110.1732 | 111.0638 |  | OLD DALBY SIDINGS |  | CCTV System | BCL/CIV/0049 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | Not fixed
|  |  | GSM4 | 110.279 | 110.1586 | Up & Down | 49 | Grimston Tunnel | Tunnel Bore | BCL/CIV/0050 | Structural Defect+I1081:AD1081 | Defects from previous detailed exam | Further deterioration of structure | Asset Management | Passengers & Workforce | Annual vissual inspection req | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Next Detailed - 2019 Colin Watson Comment: "1) Shaft 2. Ring dam is leaking. Recommend clear ring dams and down pipes of debris and repair as required. Priority 2. 2) Melton Portal, parapet. Loose and missing brickwork in areas to front and back of portal parapet. Recommend that brickwork is replaced. Priority 3. (Recommendation taken from detailed report dated 21/08/13.) 3) Melton Portal, vegetation growing to face of portal including one sapling. Recommend that vegetation is removed and roots treated to stop regrowth. Priority 3. (Recommendation taken from detailed report dated 21/08/13.) 4) Melton Portal, wing wall. Loose brickwork to top of wing wall area 3 m2. Recommend that top courses are taken down, vegetation removed and brickwork rebuilt. Priority 3. (Recommendation taken from detailed report dated 21/08/13.) 5) Melton Portal, wing wall. Loose brickwork to top of wing wall area 3 m2. Recommend that top courses are taken down, vegetation removed and brickwork rebuilt. Priority 3. (Recommendation taken from detailed report dated 21/08/13.) 6) Melton Portal, anti trespass protection for OHLE electrification appears inadequate to modern day standards. Recommend that this is reviewed and updated. Priority 2. 7) Melton Portal, anti trespass protection for OHLE electrification appears inadequate to modern day standards. Recommend that this is reviewed and updated. Priority 2. | 1 | 1 | 2 | 2019-04-01 | Ref: BCL/CIV/0239 | Closed | D Gent
|  |  | GSM4 | 111.0286 | 111.0286 |  | 48C BRICK CULVERT |  | Culvert | BCL/CIV/0051 | Deterioration of structure | vegetation and structural defect | Further deterioration of structure | Safety | Workforce | Track patrol | 2 | 3 | 5 | 2018-04-12 |  |  |  |  | Check old records for location of the structure, clear vegetation in the mileage vicinity and carry out examination exam completed, no significant defects reported | 1 | 1 | 2 | 2019-04-01 | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 111.0306 | 111.0306 | Up & Down | OLD DALBY 1 |  | UTX | BCL/CIV/0052 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | Not fixed
|  |  | GSM4 | 111.0385 | 111.0385 | Up & Down | DC SUBSTATION |  | UTX | BCL/CIV/0053 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | Not fixed
|  |  | GSM4 | 111.0418 | 111.0418 |  | 48B BRICK CULVERT |  | Culvert | BCL/CIV/0054 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 Exam completed, no significant defects recorded | 1 | 1 | 2 | 2019-04-01 | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 111.0418 | 111.0418 | Up & Down | OLD DALBY 2 |  | UTX | BCL/CIV/0055 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | Not fixed
|  |  | GSM4 | 111.0594 | 111.0594 |  | 48A BRICK CULVERT |  | Culvert | BCL/CIV/0056 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 Exam completed, no significant defects recorded | 1 | 1 | 2 | 2019-04-01 | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 111.0594 | 111.0594 | Up & Down | 48A | Pipe | Pipe | BCL/CIV/0057 | Unknown structure | No records made available | May be unknown hazards | Asset Management | Workforce | Track patrol | 2 | 2 | 4 | 2018-04-26 |  |  |  |  | Clear vegetation to allow access to structure exam carried out | 1 | 1 | 2 | 2018-10-01 | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 111.066 | 111.066 |  | Radio mast |  | Radio Mast | BCL/CIV/0058 |  | Radio Mast, no records available, visual inspection required 2018 | Unknown defects could affect line operation | Asset Management | All |  | 3 | 1 | 4 | 12/04/201: |  |  |  |  | Visual inspection required 2018 | 1 | 2 | 3 | 2018-11-01 |  | Closed | D Gent | 2018-12-01
|  |  | GSM4 | 111.0748 |  |  | 48 | Old Dalby and Broughton Road | Underbridge | BCL/CIV/0214 | Structural defect | Install new/replace bridge strike plate indicating the correct contact tel number and the ELR. | Bridge strikes go unreported | Asset Management | All | Track patrol and annual visual inspection | 1 | 3 | 4 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) Install new/replace bridge strike plate indicating the correct contact tel number and the ELR. 2) remove timber height restriction signage to road-side spandrels and replace with painted lane-width restriction indicators | 1 | 1 | 2 | 2019-04-01 |  | Closed | Network Rail | 2019-04-01 | Bridge strikes go unreported | Track patrol and annual visual inspection | Network Rail |  |  | 2019-02-07
48 | 52.6826 | -1.5064 | GSM4 | 111.0748 |  | Both | 48 | Old Dalby and Broughton Road | Underbridge | BCL/CIV/0244 | Bridge failure due to excessive vehicle loading | Bridge has been assessed as being RA10, but there is currently no vehicle restrictions and the line speed is 115mph in this section | Bridge deforms under loading leading to failure | Asset Management | All | Annual vissual inspection req | 2 | 3 | 5 | 2018-09-26 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Short term: axle weight of actuial traffic is 11tonnes Medium term: Carry out a more detailed assessment (previous was done using the L0 tool); | 1 | 1 | 2 | 2019-04-01 |  | Open | D Gent | 2018-12-01 | Bridge failure after prolongued deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 111.0748 | 111.0748 | Up & Down | 48 | Old Dalby and Broughton Road UB | Underbridge | BCL/CIV/0059 |  | DC rail on line with limited clearance over bridge, no signs | Unknown defects could affect line operation | Asset Management | All |  | 3 | 2 | 5 | 2018-04-12 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 | BCL/CIV/0214 | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 111.0748 | 111.0748 | Up & Down | 48 | Old Dalby and Broughton Road UB | Underbridge | BCL/CIV/0060 | Structural defect | Missing bridge strike plates | bridge struck and not reported | Asset Management | Members of public (MoP) | Annual vissual inspection req | 3 | 1 | 4 | 2018-04-26 |  |  |  |  | Next Detailed - 2021 Provide bridge strike plates (one has Incorrect telephone number and the other vandalised) | 1 | 1 | 2 | 2018-06-01 | BCL/CIV/0214 | Closed | D Gent | 2018-06-01
|  |  | GSM4 | 111.1144 | 111.1144 |  | 47C SEWER |  | Culvert | BCL/CIV/0061 | Deterioration of structure | vegetation and structural defect | Further deterioration of structure | Safety | Workforce | Track patrol | 2 | 3 | 5 | 2018-04-12 |  |  |  |  | Check old records for location of the structure, clear vegetation in the mileage vicinity and carry out examination exam completed, no significant defects reported | 1 | 1 | 2 |  | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 111.1386 | 111.1386 |  | 47B BRICK CULVERT |  | Culvert | BCL/CIV/0062 | Deterioration of structure | vegetation and structural defect | Further deterioration of structure | Safety | Workforce | Track patrol | 2 | 3 | 5 | 2018-04-12 |  |  |  |  | Check old records for location of the structure, clear vegetation in the mileage vicinity and carry out examination exam completed, no significant defects reported | 1 | 1 | 2 |  | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 111.1584 | 111.1584 | Up & Down | 47 | Hay's Bridge | Underbridge | BCL/CIV/0063 |  | DC rail on line with limited clearance over bridge, no signs | Unknown defects could affect line operation | Asset Management | All |  | 3 | 2 | 5 | 2018-04-12 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 | BCL/CIV/0205 | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 111.1584 | 111.1584 | Up & Down | 47 | Hay's Bridge | Underbridge | BCL/CIV/0064 | defects from detailed exam | vegetation and structural defect | deterioration of structure |  |  | Annual vissual inspection req | 3 | 1 | 4 | 2018-04-11 |  |  |  |  | 1) Remove vegetation 2) Point up, date tab and monitor Longitudinal fracture 3m long 2mm wide 3) Point up, date tab and monitor Horizontal fracture 6m long 3mm wide | 1 | 2 | 3 | 2018-11-01 | BCL/CIV/0205 | Closed | D Gent | 2018-12-01
47 | 52.8165 | -1.0014 | GSM4 | 111.1584 |  |  | 47 | Hay's Bridge | Underbridge | BCL/CIV/0205 | Structural defect | 2) Point up, date tab and monitor Longitudinal fracture 3m long 2mm wide 3) Point up, date tab and monitor Horizontal fracture 6m long 3mm wide | Unable to track bridge deterioration | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 2) Point up, date tab and monitor Longitudinal fracture 3m long 2mm wide 3) Point up, date tab and monitor Horizontal fracture 6m long 3mm wide | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Unable to track bridge deterioration | Track patrol and annual visual inspection | Network Rail
47 | 52.8165 | -1.0014 | GSM4 | 111.1584 | 111.1584 | Up & Down | 47 | Hay's Bridge | Underbridge | BCL/CIV/0243 | Bridge failure due to excessive vehicle loading | Bridge has been assessed as being RA7, but there is currently no vehicle restrictions and the line speed is 115mph in this section | Bridge deforms under loading leading to failure | Asset Management | All | Annual vissual inspection req, currently there are only 11 tonne vehicles in this section | 1 | 3 | 4 | 2018-09-26 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Treat | Short term: axle weight of actuial traffic is 11tonnes Medium term: Carry out a more detailed assessment (previous was done using the L0 tool); Determine ballast depth to backing material; Stitch cracks in barrel - previously repointed but have re-opened; | 1 | 1 | 2 | 2018-11-01 |  | Open | D Gent | 2018-12-01 | Bridge failure after prolongued deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 111.1585 | 111.1585 |  | 47A 3FT BRICK CULVERT |  | Culvert | BCL/CIV/0065 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | Detailed inspection req 2018 Examination complete | 1 | 1 | 2 |  | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 112 | 112.12 | URL | Pre-Cast concrete Retaining Wall (Units) (Approx Length 6ch) |  | Culvert | BCL/CIV/0066 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 |  |  | 0 |  |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 112.0066 | 112.0066 |  | 46A BRICK CULVERT |  | Culvert | BCL/CIV/0067 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | Detailed inspection req 2018 Examination complete | 1 | 1 | 2 |  | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 112.0176 | 112.0176 | Up & Down | 46 | Copley's Bridge UB | Underbridge | BCL/CIV/0068 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | BCL/CIV/0215 | Closed | D Gent | Not fixed
46 | 52.8183 | -1.0013 | GSM4 | 112.0176 |  |  | 46 | Copley's Bridge | Underbridge | BCL/CIV/0215 | Structural defect | Fit tabs to soffit fractures. Carry out vegetation clearance and weedspraying under bridge and around wing walls | Unable to track bridge deterioration | Asset Management | All |  | 1 | 3 | 4 | 2018-11-19 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Fit tabs to soffit fractures. Carry out vegetation clearance and weedspraying under bridge and around wing walls | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Structural failure after prolonged deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 112.0418 | 112.0418 |  | 45B BRICK CULVERT |  | Culvert | BCL/CIV/0069 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | Detailed inspection req 2018 examination complete | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 112.044 | 112.044 |  | 112/A1 | Retaining Wall | Retaining Wall | BCL/CIV/0070 |  | Retaining Wall not located at time of exam More details required |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Retaining Wall not located at time of exam More details required Retaining wall located, no significant defects reported | 1 | 1 | 2 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 112.044 | 112.044 |  | 112/A2 | Retaining Wall | Retaining Wall | BCL/CIV/0071 |  | Retaining Wall not located at time of exam More details required |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Retaining Wall not located at time of exam More details required Wall located, no significant defects recorded | 1 | 1 | 2 | 2018-08-01 | 2018 annual exam report | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 112.0704 | 112.0704 |  | 45A 3FT BRICK CULVERT |  | Culvert | BCL/CIV/0072 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | Detailed inspection req 2018 examination complete | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 112.095 | ? | URL | Low Retaining Wall (Blue Brick) (Approx length 1ch) Sth of Br 45 |  | Culvert | BCL/CIV/0073 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 exam completed | 1 | 1 | 2 |  |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 112.1 | 112.1088 | DRL | Low Retaining Wall (Blue Brick) (Approx length 4ch) Nr Br 45 |  | Culvert | BCL/CIV/0074 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 exam complete | 1 | 1 | 2 |  |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 112.1056 | 112.1056 |  |  | Retaining Wall | Retaining Wall | BCL/CIV/0075 |  | Search of records for details of asset otherwise Remove structure from work bank (unlocated) |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Search of records for details of asset otherwise Remove structure from work bank (unlocated) | 1 | 1 | 2 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 112.1078 | 112.1078 |  | 112/B1 | Retaining Wall | Retaining Wall | BCL/CIV/0076 |  |  |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Exam completed, no significant defects recorded | 1 | 1 | 2 | 2018-08-01 | 2018 annual report | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 112.1078 | 112.1078 |  | 112/B2 | Retaining Wall | Retaining Wall | BCL/CIV/0077 |  | Retaining Wall not located at time of exam More details required |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Exam completed, no significant defects recorded | 1 | 1 | 2 | 2018-08-01 | 2018 annual report | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 112.1144 | 112.1144 |  | 112/B3 | Retaining Wall | Retaining Wall | BCL/CIV/0078 |  | No records |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Exam completed, no significant defects recorded | 1 | 1 | 2 | 2018-08-01 | 2018 annual report | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 112.121 | 112.121 | Up & Down | 45 | Willoughby Road OB | Overbridge | BCL/CIV/0079 |  | DC rail on line with limited clearance beneath bridge, no signs |  |  |  |  | 3 | 2 | 5 | 2018-04-12 |  |  |  |  | Carry out visual inspection | 1 | 1 | 2 | 2018-10-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 112.121 | 112.121 | Up & Down | 45 | Willoughby Road OB | Overbridge | BCL/CIV/0080 | Detailed Exam Required | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line |  |  |  |  | 1 | 3 | 4 | 2018-04-11 |  |  |  |  | Carry out visual inspection 2018 Visual examination report has been received and reviewed and the structure is in good condition with no significant defects observed. | 1 | 1 | 2 | 2018-10-01 |  | Closed | D Gent | 2018-07-06 | Deterioration of structure | Track patrol, annual examination | BCL
45 | 52.8264 | -1.0041 | GSM4 | 112.1210 |  |  | 45 | Willoughby Road | Overbridge | BCL/CIV/0228 | Structural defect | 1) re-point local areas of open joints | Dropping brickwork on live rail traffic | Asset Management | All |  | 2 | 3 | 5 | 2018-11-19 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) re-point local areas of open joints | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Structural failure after prolonged deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 112.123 | 112.13 | URL | Pre-Cast concrete Retaining Wall (Units) (Approx Length 3ch) |  | Culvert | BCL/CIV/0081 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 |  |  | 0 |  |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 113.0198 | 113.0198 | Up & Down | 44 | Wolley's Bridge OB | Overbridge | BCL/CIV/0082 |  | DC rail on line with limited clearance beneath bridge, no signs |  |  |  |  | 3 | 2 | 5 | 2018-04-12 |  |  |  |  | Carry out visual inspection | 1 | 1 | 2 | 2018-10-01 | BCL/CIV/0206 | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 113.0198 | 113.0198 | Up & Down | 44 | Wolley's Bridge OB | Overbridge | BCL/CIV/0083 | Unable to access all parts of structure | Excessive vegetation obscuring the bridge and blocking track access beneath was identified in the 2018 examination report | Unable to inspect track, unable to reach a position of safety should a train pass whilst work is being undertaken | Safety | Workforce Health & Safety | Track patrol | 1 | 4 | 5 | 2018-07-06 |  |  |  |  | De-vegetate the side of line Confirm this has been undertaken by Next Detailed - 2020 | 1 | 1 | 2 | 2020-01-01 | BCL/CIV/0206 | Closed | D Gent | 2020-01-01
44 | 52.831 | -1.0129 | GSM4 | 113.0198 |  |  | 44 | Wolley's Bridge | Overbridge | BCL/CIV/0206 | Structural defect | Ensure topside of deck is inspected | Train or personnel struck, structural failure | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) Ensure topside of deck is inspected 2) re-point local areas of open joints | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 113.0242 | 113.0242 | Up & Down | 43D | Pipe | Pipe | BCL/CIV/0084 | Unknown structure | No records made available | May be unknown hazards | Asset Management | Workforce | Track patrol | 2 | 2 | 4 | 2018-04-26 |  |  |  |  | Carry out DE as there is no available information on this structure examination complete | 1 | 1 | 2 | 2018-10-01 | Annual exam report | Closed | D Gent | 2019-04-01
43 | 52.8329 | -1.0173 | GSM4 | 113.0337 | 113.0337 | D/S | TT09.29 | OLE Structure | OLE Equipt. | BCL/CIV/0254 | Undermining of foundation | Foundation within embankment is being undermined - Identified by NR visual exam in 2018 | Collapse of structure and failure of OLE | Performance | All | Track patrol and annual visual inspection | 1 | 4 | 5 | 2019-01-21 | Qualitative | Explicit Risk Estimation | This defect has been identified by NR examination and scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Reinstate surrounding ground with concrete The foundation is likely to be a 4m long pile, in accordance with OLEMI details and therefore is not actually being undermined. | 1 | 1 | 2 | 2020-04-01 |  | Open | Network Rail | 2020-04-01 | Failure of structure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM5 | 113.04 | 113.0466 | DRL |  | Boundary Wall (Red Brick) South of Br 43 (Approx length 3ch) | Retaining Wall | BCL/CIV/0085 |  | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | deterioration of structure | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-13 |  |  |  |  | Visual inspection req | 1 | 1 | 2 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 113.0484 | 113.0504 |  | GSM4_112_A2 - retaining wall |  | Retaining Wall | BCL/CIV/0160 | Structure not examined | Heavy vegetation obscuring structure | Structure could be in a state of dis-repair / failure | Asset Management | Passengers | Track patrol | 1 | 3 | 4 | 2018-07-19 |  |  |  |  | De-vegetate the locxation and complete the examination of the structure | 1 | 1 | 2 | 2019-02-01 |  | Closed | D Gent | 2019-02-01
|  |  | GSM4 | 113.055 | 113.055 | Up & Down | 43B | Pipe | Pipe | BCL/CIV/0086 | Unknown structure | No records made available | May be unknown hazards | Asset Management | Workforce | Track patrol | 2 | 2 | 4 | 2018-04-26 |  |  |  |  | Carry out DE as there is no available information on this structure examination complete | 1 | 1 | 2 | 2018-10-01 | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 113.055 | 113.055 | Up & Down | 43C | Pipe | Pipe | BCL/CIV/0087 | Unknown structure | No records made available | May be unknown hazards | Asset Management | Workforce | Track patrol | 2 | 2 | 4 | 2018-04-26 |  |  |  |  | Undertake viusual inspection examination complete | 1 | 1 | 2 | 2018-10-01 | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 113.055 | 113.055 |  | 113/A1 | Retaining Wall | Retaining Wall | BCL/CIV/0088 |  | No records |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Exam completed, no significant defects recorded | 1 | 1 | 2 | 2018-08-01 | 2018 annual report | closed | D Gent | 2018-08-01
|  |  | GSM4 | 113.0616 | 113.0616 |  | 113/A2 | Retaining Wall | Retaining Wall | BCL/CIV/0089 |  | No records |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Exam completed, no significant defects recorded | 1 | 1 | 2 | 2018-08-01 | 2018 annual report | closed | D Gent | 2018-08-01
|  |  | GSM4 | 113.0682 | 113.0682 | Up & Down | 43A | Side of line bridge | Overbridge | BCL/CIV/0090 | [5 empty] | Annual vissual inspection req | 3 | 1 | 4 | 2018-04-11 |  |  |  |  | Next Detailed - 2023 examination complete | 1 | 1 | 2 | 2018-10-01 | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 113.0682 | 113.0682 | Up & Down | 43 | Folly Hall Bridge | Overbridge | BCL/CIV/0091 | [5 empty] | Annual vissual inspection req | 3 | 1 | 4 | 2018-04-11 |  |  |  |  | Next Detailed - 2023 | 1 | 1 | 2 | 2018-10-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 113.0682 | 113.0682 |  | 43A | Side of line bridge | Side of line Bridge | BCL/CIV/0092 |  | No records |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | examination complete | 1 | 1 | 2 | 2018-08-01 | Annual exam report | Closed | D Gent | 2018-08-01
43 | 52.8329 | -1.0173 | GSM4 | 113.0682 |  |  | 43 | Folly Hall Bridge | Overbridge | BCL/CIV/0216 | Structural defect | Remove vegetation and ivy | Unable to track bridge deterioration | Asset Management | All |  | 1 | 3 | 4 | 2018-11-19 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Remove vegetation and ivy | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Structural failure after prolonged deterioration | Track patrol and annual visual inspection | Network Rail
43 | 52.8329 | -1.0173 | GSM4 | 113.0772 | 113.0772 | U/S | TT10.04 | OLE Strcuture | OLE Equipt. | BCL/CIV/0255 | Undermining of foundation | Foundation within embankment is being undermined - Identified by NR visual exam in 2018 | Collapse of structure and failure of OLE | Performance | All | Track patrol and annual visual inspection | 1 | 4 | 5 | 2019-01-21 | Qualitative |  | This defect has been identified by NR examination and scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Reinstate surrounding ground with concrete The foundation is likely to be a 4m long pile, in accordance with OLEMI details and therefore is not actually being undermined. | 1 | 1 | 2 | 2020-04-01 |  | Open | Network Rail | 2020-04-01 | Failure of structure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 113.1474 | 113.1474 |  | 42A 3FT BRICK CULVERT |  | Culvert | BCL/CIV/0093 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | Detailed inspection Examination completed | 1 | 1 | 2 | 2018-04-01 | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 113.1496 | 113.1496 | Up & Down | 42 | Warren's Senior Bridge UB | Underbridge | BCL/CIV/0094 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure Exam completed, no significant defects identified | 1 | 1 | 2 | 2019-04-01 | Annual exam report | Closed | D Gent | Not fixed
|  |  | GSM4 | 114.0066 | 114.0066 |  | 41A BRICK CULV WITH 400MM PLASTIC PIPE THRO' |  | Culvert | BCL/CIV/0095 | Missing safety fence | Safety defect | Falls from height | Safety | Workforce | Track patrol | 2 | 5 | 7 | 2018-04-26 |  |  |  |  | Visually inspect structure and replace missing fence if required | 1 | 1 | 2 | 2018-09-01 |  | Closed | D Gent | 2018-10-01
41A | 52.841 | -1.0261 | GSM4 | 114.0066 |  |  | 41A | Culvert | Culvert | BCL/CIV/0240 | Structural defect | 2) Install safety fence | Injury to personnel | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 2) Install safety fence | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Injury to personnel | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 114.0308 | 114.0308 | Up & Down | 41 | Warren's Junior Bridge | Underbridge | BCL/CIV/0096 |  | Coping stones displaced |  |  |  |  | 3 | 2 | 5 | 2018-04-12 |  |  |  |  | re-seat displaced coping stones | 1 | 1 | 2 | 2018-10-01 | BCL/CIV/0241 | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 114.0308 | 114.0308 | Up & Down | 41 | Warren's Junior Bridge UB | Underbridge | BCL/CIV/0097 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | BCL/CIV/0241 | Closed | D Gent | Not fixed
41 | 52.841 | -1.0261 | GSM4 | 114.0308 |  |  | 41 | Warren's Junior Bridge | Underbridge | BCL/CIV/0241 | Structural defect | Re-seat displaced copings to SW wing wall | Injury to personnel | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-19 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Re-seat displaced copings to SW wing wall | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 114.0396 | 114.0396 |  | 40A BRICK CULVERT |  | Culvert | BCL/CIV/0098 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 Exam completed, no significant defects recorded | 1 | 1 | 2 | 2019-04-01 | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 114.0484 | 114.0484 | Up & Down | 40 | Underbridge | Underbridge | BCL/CIV/0099 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure Exam completed, no significant defects identified | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | 2018-11-20
|  |  | GSM4 | 114.0814 | 114.0814 | Up & Down | 39 | Roe's Bridge UB | Underbridge | BCL/CIV/0100 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure Exam completed, no significant defects identified | 1 | 1 | 2 | 2019-04-01 | Annual exam report | Closed | D Gent | Not fixed
|  |  | GSM4 | 114.1166 | 114.1166 |  |  | Retaining Wall | Retaining Wall | BCL/CIV/0101 |  | No records |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 | [5 empty] | 1 | 1 | 2 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 114.1166 | 114.1166 |  |  | Retaining Wall | Retaining Wall | BCL/CIV/0102 |  | No records |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 | [5 empty] | 1 | 1 | 2 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 114.1209 | 114.1209 |  | 38A BRICK CULVERT |  | Culvert | BCL/CIV/0103 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 Exam completed, no significant defects recorded | 1 | 1 | 2 | 2019-04-01 | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 114.121 | 114.121 | Up & Down | 38A | Pipe | Pipe | BCL/CIV/0104 | Unknown structure | No records made available | May be unknown hazards | Asset Management | Workforce | Track patrol | 2 | 2 | 4 | 2018-04-26 |  |  |  |  | Remove from Task Schedule | 1 | 1 | 2 | 2018-10-01 |  |  | D Gent | 2019-04-01
38 | 52.8492 | -1.0333 | GSM4 | 114.1210 |  |  | 38 | Fosse Road | Underbridge | BCL/CIV/0242 | Structural defect | 1) Undertake concrete repairs to areas of spalling to base of pier, include for treating any exposed reinforcing. 2) Replace bridge strike signage with correct phone numbers. 3) Provide limited clearance signage along track at both ends | Bridge strikes go unreported | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) Undertake concrete repairs to areas of spalling to base of pier, include for treating any exposed reinforcing. 2) Replace bridge strike signage with correct phone numbers. - strrike plates replaced on 8/2/19 3) Provide limited clearance signage along track at both ends | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Bridge strikes go unreported | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 114.121 | 114.121 | Up & Down | 38 | Fosse Road - A46 UB | Underbridge | BCL/CIV/0105 | Unrecorded structure defects | Limited clearance both lines, no limited clearance signs |  | Safety |  | Track patrol, No red zone working | 3 | 3 | 6 | 2018-04-11 |  |  |  |  | Carry out inspection in the first instance to determine level of risk, implement a safe system of work | 1 | 2 | 3 | 2018-08-01 | BCL/CIV/0242 | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 114.121 | 114.121 | Up & Down | 38 | Fosse Road - A46 UB | Underbridge | BCL/CIV/0106 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | BCL/CIV/0242 | Closed | D Gent | Not fixed
37 | 52.8528 | -1.0362 | GSM4 | 114.1672 |  |  | 37 | Hollingworth's Bridge | Overbridge | BCL/CIV/0207 | Structural defect | Repair vertical fracture located at High Mileage Downside of track parapet face | Train or personnel struck, structural failure | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Repair vertical fracture located at High Mileage Downside of track parapet face | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 114.1672 | 114.1672 | Up & Down | 37 | Hollingworth's Bridge OB | Overbridge | BCL/CIV/0107 | [5 empty] | Visual examination record has been received, no significant defects that require actioning | 1 | 1 | 2 | 2018-04-11 |  |  |  |  | Next Detailed - 2022 | 1 | 1 | 2 | 2018-10-01 |  | closed | D Gent | 2019-04-01
|  |  | GSM4 | 115 | 115 |  | Widmerpool Station |  | Building | BCL/CIV/0108 | No inspection report | there is no inspection report so we currently have no idea of the strcutural condition |  | Safety | All |  | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | Undertake structural inspection | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | Not set
|  |  | GSM4 | 115.022 | 115.022 |  | 36A BRICK CULVERT |  | Culvert | BCL/CIV/0109 | Deterioration of structure | vegetation and structural defect | Further deterioration of structure | Safety | Workforce | Track patrol | 2 | 3 | 5 | 2018-04-12 |  |  |  |  | Check old records for location of the structure, clear vegetation in the mileage vicinity and carry out examination exam completed, no significant defects reported | 1 | 1 | 2 |  | Annual exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 115.0396 | ? | DRL | Wimerpool old station Platform wall Upside (Approx length 4ch) |  | Culvert | BCL/CIV/0110 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 |  |  | 0 |  |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 115.0484 | 115.0484 | Up & Down | 36 | Widmerpool Station OB | Overbridge | BCL/CIV/0111 | [5 empty] | Annual vissual inspection req | 3 | 1 | 4 | 2018-04-11 |  |  |  |  | Next Detailed - 2023 | 1 | 1 | 2 | 2018-10-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 115.066 | 115.066 |  |  | Retaining Wall | Retaining Wall | BCL/CIV/0112 |  | No records |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 | [5 empty] | 1 | 1 | 2 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 115.0851 | 115.0851 | Up & Down | OB35 |  | UTX | BCL/CIV/0113 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | BCL/CIV/0218 | Closed | D Gent | Not fixed
|  |  | GSM4 | 115.0858 | 115.0858 | Up & Down | 35 | Newbound's Bridge OB | Overbridge | BCL/CIV/0114 | Deterioration due to vegetation | Heavy vegetation obscuring structure | Excellorated deterioration | Asset Management | Workforce | Annual vissual inspection req | 3 | 2 | 5 | 2018-04-11 |  |  |  |  | Carry out de-vegetation works prior to next visual exam. Next Detailed - 2022 | 1 | 1 | 2 | 2019-04-01 | BCL/CIV/0218 | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 115.0858 | 115.0858 | Up & Down | 35 | Newbound's Bridge | Overbridge | BCL/CIV/0115 | Unrecorded structure defects | Parapet fracture requires inspection | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-11 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 | BCL/CIV/0218 | Closed | D Gent | 2018-08-01
35 | 52.86 | -1.042 | GSM4 | 115.0858 |  |  | 35 | Newbound's Bridge | Overbridge | BCL/CIV/0218 | Structural defect | Fit further tabs to parapet fractures and monitor | Unable to track bridge deterioration | Asset Management | All |  | 1 | 3 | 4 | 2018-11-19 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Fit further tabs to parapet fractures and monitor | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Structural failure after prolonged deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 115.089 | 115.089 | Up & Down | OB35 |  | UTX | BCL/CIV/0116 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | BCL/CIV/0218 | Closed | D Gent | Not fixed
|  |  | GSM4 | 115.11 | 115.11 |  |  | Retaining Wall | Retaining Wall | BCL/CIV/0117 |  | Provide structure number including ELR (ID plate)on the wall or adjacent to it |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Provide structure number including ELR (ID plate)on the wall or adjacent to it | 1 | 1 | 2 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 115.11 | 115.11 | Up & Down | 34 | Parish Boundary Stream Bridge | Underbridge | BCL/CIV/0118 | Detailed Exam Required | The structure has not been inspected due to silt blocking the culvert. The culvert is blocked and not functional | Unknown defects could affect line operation | Asset Management | All | Track patrol | 1 | 3 | 4 | 2018-05-18 |  |  |  |  | Complete silt removal to enable inspection, then complete inspection. | 1 | 2 | 3 | 2018-08-01 | BCL/CIV/0217 | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 115.1100 |  |  |  | Retaining Wall | Retaining Wall | BCL/CIV/0208 | Structural defect | Provide structure number including ELR (ID plate)on the wall or adjacent to it | Structure misidentified | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 |  |  |  |  | Provide structure number including ELR (ID plate)on the wall or adjacent to it | 1 | 1 | 2 | 2019-04-01 |  | closed | Network Rail | 2019-04-01 | Structure misidentified | Track patrol and annual visual inspection | Network Rail
34 | 52.8609 | -1.0449 | GSM4 | 115.1100 |  |  | 34 | Underbridge | Underbridge | BCL/CIV/0217 | Structural defect | Vegetation to be cleared in watercourse around bridge Investigate slight horizontal displacement of training wall on Down side as part of 2018 examination | Unable to track bridge deterioration | Asset Management | All |  | 1 | 3 | 4 | 2018-11-19 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Vegetation to be cleared in watercourse around bridge Investigate slight horizontal displacement of training wall on Down side as part of 2018 examination | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Structural failure after prolonged deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 115.1122 | 115.1122 |  |  | Retaining Wall | Retaining Wall | BCL/CIV/0119 |  | Provide structure ID plate (wall length=7m, Height=0.3m) |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Provide structure ID plate (wall length=7m, Height=0.3m) | 1 | 1 | 2 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 115.1122 |  |  |  | Retaining Wall | Retaining Wall | BCL/CIV/0209 | Structural defect | Provide structure ID plate | Structure misidentified | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 |  |  |  |  | Provide structure ID plate | 1 | 1 | 2 | 2019-04-01 |  | Closed | Network Rail | 2019-04-01 | Structure misidentified | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 115.1451 | 115.1451 |  | 1151451 2FT CULVERT UNDER APPROACH TO BR NO 33 |  | Culvert | BCL/CIV/0120 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 Exam completed, no significant defects recorded | 2 | 1 | 3 | 2019 | 2018 Annual Exam report | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 115.1516 | 115.1606 | URL | Pre-Cast concrete Retaining Wall (Units) |  | Culvert | BCL/CIV/0121 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 |  |  | 0 |  |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 115.1643 | 106.1212 |  | Radio mast |  | Radio Mast | BCL/CIV/0122 | Unrecorded structure defects | Radio Mast, no records available, visual inspection required 2018 | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 1 | 4 | 12/04/201: |  |  |  |  | Visual inspection required 2018 | 1 | 2 | 3 | 2018-11-01 |  | Closed | D Gent | 2018-12-01
|  |  | GSM4 | 115.1643 | 116.1212 | Up & Down | 32 | Stanton Tunnel | Tunnel Bore | BCL/CIV/0123 | Structural Defect+I1081:AD1081 | Defects from previous detailed exam | Further deterioration of structure | Asset Management | Passengers & Workforce | Annual vissual inspection req | 3 | 2 | 5 | 2018-04-26 |  |  |  |  | Next Detailed - 2019 Colin Watson Comment: 1) Edwalton Portal, anti trespass protection for OHLE electrification appears inadequate to modern day standards. Also 2 No. timbers missing to parapet. Recommend existing boarding is removed and palisade fencing is fitted to rear of parapet with returns to Chevaux de Frise. Priority 1. 2) Melton Portal, anti trespass protection for OHLE electrification appears inadequate to modern day standards. Also 8 No. timbers missing to parapet. Recommend existing boarding is removed and palisade fencing is fitted to rear of parapet with returns to Chevaux de Frise. Priority 1. 3) Edwalton portal drainage flume. Tree growing to drainage flume, girth 1.2 m. Recommend tree is removed and drainage flumes are cleared of all vegetation. Priority 1 4) Shaft 3 base of shaft. Timber grillage showing signs of rot and generally in poor condition. Recommend that timber grillage is removed. Priority 1. (Recommendation taken from detailed report dated 05/08/13.) 5) Shaft 2 base of shaft. Timber grillage showing signs of rot and generally in poor condition. Recommend that timber grillage is removed. Priority 1. (Recommendation taken from detailed report dated 05/08/13.) 6) Shaft 1 base of shaft. Timber grillage showing signs of rot and generally in poor condition. Recommend that timber grillage is removed. Priority 1. (Recommendation taken from detailed report dated 05/08/13.) 7) Shaft 1 head wall. Top 10 courses of headwall show loose and missing brickwork with tree growth, area 10 m2. Recommend that coping stones are removed, top courses are taken down and rebuilt and coping stones are replaced. Priority 3. (Recommendation taken from detailed report dated 05/08/13.) 8) Melton Portal, drainage. Outlet is blocked and there is a partial collapse of the drain culvert. Recommend that blockage is cleared and brickwork to end of culvert is replaced. All flumes and drainage channels to be cleared of vegetation. Priority 2. 9) Edwalton Portal, loose brickwork to full height of newel. Area 2 m2. Take down loose brickwork and replace. Priority 3. (Recommendation taken from detailed report dated 05/08/13.) 10) Melton Portal, loose and missing brickwork to pilaster. Area 2 m2. Take down loose brickwork and replace. Priority 3. (Recommendation taken from detailed report dated 05/08/13.) 11) Edwalton Portal, loose and missing brickwork to pilaster. Area 2 m2. Take down loose brickwork and replace. Priority 2. | 1 | 1 | 2 | 2019-04-01 | Ref: BCL/CIV/0247 | Closed | D Gent | 2018-04-01
|  |  | GSM4 | 116.0054 | 116.0054 | Up & Down | 32 | Stanton Tunnel Shaft 1 (Open) | Tunnel Shaft | BCL/CIV/0124 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | Ref: BCL/CIV/0247 | Closed | D Gent | Not fixed
|  |  | GSM4 | 116.0583 | 116.0583 | Up & Down | 32 | Stanton Tunnel Shaft 2 (Open) | Tunnel Shaft | BCL/CIV/0125 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | Ref: BCL/CIV/0247 | Closed | D Gent | Not fixed
32 | 52.8646 | -1.0478 | GSM4 | 116.088 |  | Both | 32 | Stanton Tunnel | Tunnel | BCL/CIV/0247 | Structural defect | 2) Melton Portal, anti trespass protection for OHLE electrification appears inadequate to modern day standards. Also 8 No. timbers missing to parapet. Recommend existing boarding is removed and palisade fencing is fitted to rear of parapet with returns to Chevaux de Frise. Priority 1. 3) Edwalton portal drainage flume. Tree growing to drainage flume, girth 1.2 m. Recommend tree is removed and drainage flumes are cleared of all vegetation. Priority 1 4) Shaft 3 base of shaft. Timber grillage showing signs of rot and generally in poor condition. Recommend that timber grillage is removed. Priority 1. (Recommendation taken from detailed report dated 05/08/13.) 5) Shaft 2 base of shaft. Timber grillage showing signs of rot and generally in poor condition. Recommend that timber grillage is removed. Priority 1. (Recommendation taken from detailed report dated 05/08/13.) 6) Shaft 1 base of shaft. Timber grillage showing signs of rot and generally in poor condition. Recommend that timber grillage is removed. Priority 1. (Recommendation taken from detailed report dated 05/08/13.) 7) Shaft 1 head wall. Top 10 courses of headwall show loose and missing brickwork with tree growth, area 10 m2. Recommend that coping stones are removed, top courses are taken down and rebuilt and coping stones are replaced. Priority 3. (Recommendation taken from detailed report dated 05/08/13.) 8) Melton Portal, drainage. Outlet is blocked and there is a partial collapse of the drain culvert. Recommend that blockage is cleared and brickwork to end of culvert is replaced. All flumes and drainage channels to be cleared of vegetation. Priority 2. 9) Edwalton Portal, loose brickwork to full height of newel. Area 2 m2. Take down loose brickwork and replace. Priority 3. (Recommendation taken from detailed report dated 05/08/13.) 10) Melton Portal, loose and missing brickwork to pilaster. Area 2 m2. Take down loose brickwork and replace. Priority 3. (Recommendation taken from detailed report dated 05/08/13.) 11) Edwalton Portal, loose and missing brickwork to pilaster. Area 2 m2. Take down loose brickwork and replace. Priority 2. | Structural failure after prolonged deterioration | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 2) Melton Portal, anti trespass protection for OHLE electrification appears inadequate to modern day standards. Also 8 No. timbers missing to parapet. Recommend existing boarding is removed and palisade fencing is fitted to rear of parapet with returns to Chevaux de Frise. Priority 1. 3) Edwalton portal drainage flume. Tree growing to drainage flume, girth 1.2 m. Recommend tree is removed and drainage flumes are cleared of all vegetation. Priority 1 4) Shaft 3 base of shaft. Timber grillage showing signs of rot and generally in poor condition. Recommend that timber grillage is removed. Priority 1. (Recommendation taken from detailed report dated 05/08/13.) 5) Shaft 2 base of shaft. Timber grillage showing signs of rot and generally in poor condition. Recommend that timber grillage is removed. Priority 1. (Recommendation taken from detailed report dated 05/08/13.) 6) Shaft 1 base of shaft. Timber grillage showing signs of rot and generally in poor condition. Recommend that timber grillage is removed. Priority 1. (Recommendation taken from detailed report dated 05/08/13.) 7) Shaft 1 head wall. Top 10 courses of headwall show loose and missing brickwork with tree growth, area 10 m2. Recommend that coping stones are removed, top courses are taken down and rebuilt and coping stones are replaced. Priority 3. (Recommendation taken from detailed report dated 05/08/13.) 8) Melton Portal, drainage. Outlet is blocked and there is a partial collapse of the drain culvert. Recommend that blockage is cleared and brickwork to end of culvert is replaced. All flumes and drainage channels to be cleared of vegetation. Priority 2. 9) Edwalton Portal, loose brickwork to full height of newel. Area 2 m2. Take down loose brickwork and replace. Priority 3. (Recommendation taken from detailed report dated 05/08/13.) 10) Melton Portal, loose and missing brickwork to pilaster. Area 2 m2. Take down loose brickwork and replace. Priority 3. (Recommendation taken from detailed report dated 05/08/13.) 11) Edwalton Portal, loose and missing brickwork to pilaster. Area 2 m2. Take down loose brickwork and replace. Priority 2. | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Structural failure after prolonged deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 116.0933 | 116.0933 | Up & Down | 32 | Stanton Tunnel Shaft 3 (Open) | Tunnel Shaft | BCL/CIV/0126 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | Ref: BCL/CIV/0247 | Closed | D Gent | Not fixed
116/A1 | 52.8745 | -1.058 | GSM4 | 116.1232 | 116.1232 |  | 116/A1 | Retaining Wall | Retaining Wall | BCL/CIV/0127 |  | Provide structure number including ELR (ID plate) on the wall or adjacent to it |  | Asset Management | Workforce | Track patrol | 2 | 2 | 4 | 2018-04-26 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Provide structure number including ELR (ID plate) on the wall or adjacent to it | 3 | 1 | 4 | 2019-04-01 |  | Open | D Gent | 2018-08-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 116.1232 |  |  |  | Retaining Wall | Retaining Wall | BCL/CIV/0210 | Structural defect | Provide structure number including ELR (ID plate) on the wall or adjacent to it | Misidentification of structure | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 |  |  |  |  | Provide structure number including ELR (ID plate) on the wall or adjacent to it | 1 | 1 | 2 | 2019-04-01 |  | Closed | Network Rail | 2019-04-01 | Misidentification of structure | Track patrol and annual visual inspection | Network Rail
31A | 52.8763 | -1.0594 | GSM4 | 116.1540 |  |  | 31A | Culvert | Culvert | BCL/CIV/0219 | Structural defect | Clear debris and carry out DE (no previous information available) | Structural failure due to unrecorded defects | Asset Management | All | Track patrol and annual visual inspection | 2 | 2 | 4 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Clear debris and carry out DE (no previous information available) | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Structural failure due to unrecorded defects | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 116.7 | 116.7 |  | 31A | Brick Culvert | Culvert | BCL/CIV/0128 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-26 |  |  |  |  | visual inspection req 2018 | 1 | 1 | 2 |  | BCL/CIV/0219 | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 117.0022 | 117.0022 | Up & Down | 31 | Page's Bridge OB | Overbridge | BCL/CIV/0129 | Deterioration due to vegetation | Heavy vegetation obscuring structure | Excellorated deterioration | Asset Management | Workforce | Annual vissual inspection req | 3 | 2 | 5 | 2018-07-17 |  |  |  |  | Undertake de-vegetation works prior to next visual exam. | 1 | 1 | 2 | 2018-07-17 | BCL/CIV/0220 | Closed | D Gent | 2018-07-17
31 | 52.8791 | -1.0609 | GSM4 | 117.0022 |  |  | 31 | Page's Bridge | Overbridge | BCL/CIV/0220 | Structural defect | Carry out vegetation clearance and weedspraying to topside of bridge | Unable to track bridge deterioration | Asset Management | All |  | 1 | 3 | 4 | 2018-11-19 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Carry out vegetation clearance and weedspraying to topside of bridge | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Structural failure after prolonged deterioration | Track patrol and annual visual inspection | Network Rail
30 | 52.88 | -1.0623 | GSM4 | 117.0132 |  |  | 30 | Holbrook's Bridge | Overbridge | BCL/CIV/0221 | Structural defect | 1) Consider further re-casing of small isolated spalling | Bridge failure after prolongued deterioration | Asset Management | All | Track patrol and annual visual inspection | 2 | 2 | 4 | 2018-11-19 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) Consider further re-casing of small isolated spalling | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Structural failure after prolonged deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 117.0132 | 117.0132 | Up & Down | 30 | Holbook's Bridge OB | Overbridge | BCL/CIV/0130 | [5 empty] | Annual vissual inspection req | 3 | 1 | 4 | 2018-04-11 |  |  |  |  | Next Detailed - 2023 | 1 | 1 | 2 | 2018-10-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 117.0374 | 117.0374 |  | 29A BRICK CULVERT |  | Culvert | BCL/CIV/0131 | Missing ID plate | Structural defect | Hard to identify structure | Safety | Workforce | Track patrol | 2 | 1 | 3 | 2018-04-26 |  |  |  |  | Install/provide structure ID plate | 1 | 1 | 2 |  | BCL/CIV/0212 | closed | D Gent | 2019-04-01
29A | 52.88 | -1.0653 | GSM4 | 117.0374 |  |  | 29A | Culvert | Culvert | BCL/CIV/0212 | Structural defect | Install/provide structure ID plate | Misidentification of structure | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Install/provide structure ID plate | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Misidentification of structure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 117.0528 | 117.0528 | Up & Down | 29B | Pipe | Pipe | BCL/CIV/0132 | Unknown structure | No records made available | May be unknown hazards | Asset Management | Workforce | Track patrol | 2 | 2 | 4 | 2018-04-26 |  |  |  |  | Search of records for details of asset otherwise Remove structure from work bank (unlocated) exam completed | 1 | 1 | 2 | 2018-10-01 | Annual exam report | closed | D Gent | 2019-04-01
29 | 52.8818 | -1.0682 | GSM4 | 117.0748 |  |  | 29 | Burton's Bridge | Overbridge | BCL/CIV/0222 | Structural defect | Carry out vegetation clearance and weedspraying to topside of bridge | Unable to track bridge deterioration | Asset Management | All |  | 1 | 3 | 4 | 2018-11-19 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Carry out vegetation clearance and weedspraying to topside of bridge | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Structural failure after prolonged deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 117.0748 | 117.0748 | Up & Down | 29 | Burton's Bridge OB | Overbridge | BCL/CIV/0133 | Deterioration due to vegetation | Heavy vegetation obscuring structure | Excellorated deterioration | Asset Management | Workforce | Annual vissual inspection req | 3 | 2 | 5 | 2018-07-17 |  |  |  |  | Undertake de-vegetation works prior to next visual exam. Next Detailed - 2023 | 1 | 1 | 2 | 2019-04-01 | BCL/CIV/0222 | closed | D Gent | 2019-04-01
|  |  | GSM4 | 117.076 | 117.076 | Up & Down | OB29 |  | UTX | BCL/CIV/0134 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | BCL/CIV/0222 | Closed | D Gent | Not fixed
|  |  | GSM4 | 117.1364 | 117.1364 |  | 28A BRICK CULVERT |  | Culvert | BCL/CIV/0135 | Missing ID plate | Structural defect | Hard to identify structure | Safety | Workforce | Track patrol | 2 | 1 | 3 | 2018-04-26 |  |  |  |  | Install/provide structure ID plate | 1 | 1 | 2 |  | BCL/CIV/0213 | closed | D Gent | 2019-04-01
28A | 52.8837 | -1.0756 | GSM4 | 117.1364 |  |  | 28A | Culvert | Culvert | BCL/CIV/0213 | Structural defect | Install/provide structure ID plate | Misidentification of structure | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Install/provide structure ID plate | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Misidentification of structure | Track patrol and annual visual inspection | Network Rail
28 | 52.8837 | -1.0771 | GSM4 | 117.1386 |  |  | 28 | Normanton Lane | Underbridge | BCL/CIV/0211 | Structural defect | Install new ID plate | Misidentification of structure | Asset Management | All | Track patrol and annual visual inspection | 1 | 2 | 3 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Install new ID plate | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Misidentification of structure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 117.1386 | 117.1386 | Up & Down | 28 | Normanton Lane UB | Underbridge | BCL/CIV/0136 | Detailed Exam Required | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Unknown defects could affect line operation | Asset Management | All | Track patrol | 1 | 3 | 4 | 2018-04-11 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 | BCL/CIV/0211 | closed | D Gent | 2018-08-01
|  |  | GSM4 | 118.0374 | 118.0374 | Up & Down | 27 | Keyworth Lane UB | Underbridge | BCL/CIV/0137 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | Ref: BCL/CIV/0229 | closed | D Gent | Not fixed
|  |  | GSM4 | 118.0374 |  |  | 27 | Keyworth Lane | Underbridge | BCL/CIV/0229 | Structural defect | Install new ID plate, remove bridge strike H-frame and re-paint | Misidentification of structure | Safety | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) Install new ID plate 2) remove timber height restriction signage to road-side spandrels and replace with painted lane-width restriction indicators Strike Plates Installed 07/02/2019 | 1 | 1 | 2 | 2019-04-01 |  | Closed | Network Rail | 2019-04-01 | Misidentification of structure | Track patrol and annual visual inspection | Network Rail |  |  | 2019-02-07
|  |  | GSM4 | 118.0702 | 118.0702 | Up & Down | 26 | Burton's Bridge UB | Underbridge | BCL/CIV/0138 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | Ref: BCL/CIV/0223 | closed | D Gent | Not fixed
26 | 52.8865 | -1.0904 | GSM4 | 118.0704 |  |  | 26 | Burton's Bridge | Underbridge | BCL/CIV/0223 | Structural defect | 1) Recase spalled areas 2) Remove vegetation | Bridge failure after prolongued deterioration | Asset Management | All | Track patrol and annual visual inspection | 2 | 2 | 4 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) Recase spalled areas 2) Remove vegetation | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Bridge failure after prolongued deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 118.099 | 118.099 | Up & Down | 25 | Radmore Lane UB | Underbridge | BCL/CIV/0139 | Unrecorded structure defects | Drummy brickwork | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 1 | 4 | 2018-04-12 |  |  |  |  | Investigation into drummy brickwork required | 1 | 2 | 3 | 2018-11-01 | Ref:BCL/CIV/0230 | closed | D Gent | 2018-12-01
|  |  | GSM4 | 118.099 | 118.099 | Up & Down | 25 | Radmore Lane UB | Underbridge | BCL/CIV/0140 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | Ref:BCL/CIV/0230 | closed | D Gent | Not fixed
25 | 52.8883 | -1.0934 | GSM4 | 118.099 |  |  | 25 | Bradmore Lane | Underbridge | BCL/CIV/0230 | Structural defect | 1) remove timber height restriction signage to road-side spandrels and replace with painted lane-width restriction indicators | Pedestrians or vehicles struck by debris | Safety | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-19 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) remove timber height restriction signage to road-side spandrels and replace with painted lane-width restriction indicators | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | None | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 118.0992 | 118.0992 |  | 1180992 3FT BRICK CULVERT ADJ NO 25 |  | Culvert | BCL/CIV/0141 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018, exam completed, no significant defects recorded | 1 | 1 | 2 | 2019-04-01 |  | Closed | D Gent | 2019-04-01
|  |  | GSM4 | 118.1342 | 118.1342 | Up & Down | 24 | Brasby's Bridge UB | Underbridge | BCL/CIV/0142 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure Exam completed, no significant defects identified | 1 | 1 | 2 | 2019-04-01 | Annual exam report | Closed | D Gent | Not fixed
23 | 52.891 | -1.0993 | GSM4 | 118.1562 |  | Both | 23 | Underbridge | Underbridge | BCL/CIV/0231 | Structural defect | 1) Repair collapsed approach fencing 2 )Install new ID plate or correct the telephone number 3) remove timber height restriction signage to road-side spandrels and replace with painted lane-width restriction indicators | Bridge failure after prolongued deterioration, Misidentification of structure, pedestrians or vehicles struck by debris | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) Repair collapsed approach fencing 2 )Install new ID plate or correct the telephone number 3) remove timber height restriction signage to road-side spandrels and replace with painted lane-width restriction indicators | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Bridge failure after prolongued deterioration, Misidentification of structure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 118.1562 | 118.1562 | Up & Down | 23 | Holme's Bridge UB | Underbridge | BCL/CIV/0143 | Defect from previous detailed exam | Structural defect | Falling from height | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-26 |  |  |  |  | 1) Repair collapsed approach fencing 2 )Install new ID plate or correct the telephone number | 1 | 2 | 3 | 2018-11-01 | ref: BCL/CIV/0231 | Closed | D Gent | 2018-12-01
|  |  | GSM4 | 118.1562 | 118.1562 | Up & Down | 23 | Holme's Bridge UB | Underbridge | BCL/CIV/0144 | Unrecorded structure defects | Cast iron underbridge, pay extra attention | Structure failure | Safety | Passengers & Workforce | Track patrol | 2 | 3 | 5 | 2018-04-27 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 | ref: BCL/CIV/0231 | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 118.1562 | 118.1562 | Up & Down | 23 | Holme's Bridge UB | Underbridge | BCL/CIV/0145 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure | 1 | 1 | 2 | 2019-04-01 | ref: BCL/CIV/0231 | Closed | D Gent | Not fixed
|  |  | GSM4 | 119.0418 | 119.0418 |  |  | Retaining Wall | Retaining Wall | BCL/CIV/0146 |  | No records |  | Asset Management | Workforce | Track patrol | 3 | 2 | 5 | 2018-04-26 | [5 empty] | 1 | 1 | 2 | 2018-08-01 |  | Closed | D Gent | 2018-08-01
22 | 52.8956 | -1.1036 | GSM4 | 119.0418 |  |  | 22 | Underbridge | Underbridge | BCL/CIV/0227 | Structural defect | 1) Point up and date tab fracture to L/M abutment. 2) Point up loose brickwork and open joints to L/M D/S spandrel. 3) Point up and date tab fracture to D/S end of barrel. 4) Repair handrailing along upside. 5) Clear vegetation around structure. | Unable to track bridge deterioration | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) Point up and date tab fracture to L/M abutment. 2) Point up loose brickwork and open joints to L/M D/S spandrel. 3) Point up and date tab fracture to D/S end of barrel. 4) Repair handrailing along upside. 5) Clear vegetation around structure. | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Unable to track bridge deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 119.0418 | 119.0418 | Up & Down | 22 | Gadd's Bridge UB | Underbridge | BCL/CIV/0147 | Defects from previous detailed exam | Structural defect | deterioration of structure | Asset Management | Passengers & Workforce | Annual vissual inspection req | 3 | 1 | 4 | 2018-04-26 |  |  |  |  | Next Detailed - 2022 1) Point up and date tab fracture to L/M abutment. 2) Point up loose brickwork and open joints to L/M D/S spandrel. 3) Point up and date tab fracture to D/S end of barrel. 4) Repair handrailing along upside. 5) Clear vegetation around structure. | 1 | 1 | 2 | 2018-06-01 | ref: BCL/CIV/0227 | Closed | D Gent | 2018-06-01
|  |  | GSM4 | 119.066 | 119.066 | Up & Down | 21 | Holbrook's Bridge UB | Underbridge | BCL/CIV/0148 | Uninspected structure | No inspection report | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 2 | 5 | 2018-04-30 |  |  |  |  | request records from NR and/or complete a visual inspection of the structure Exam completed, no significant defects identified | 1 | 1 | 2 | 2019-04-01 | Annual exam report | Closed | D Gent | Not fixed
|  |  | GSM4 | 119.0924 | 119.0924 |  | 20A GREATMOOR BROOK |  | Culvert | BCL/CIV/0149 | Defective vegetation | Vegetation defect | Further deterioration of structure | Safety | Workforce | Track patrol | 2 | 3 | 5 | 2018-04-26 |  |  |  |  | 1) Remove veg and reposition displaced brickwork on H/M downside wall. 2) Cut down tree and treat to prevent regrowth on L/M upside wall. | 1 | 1 | 2 | 2019-04-01 | ref: BCL/CIV/0226 | Closed | D Gent | 2019-04-01
20A | 52.8983 | -1.108 | GSM4 | 119.0924 |  |  | 20A | Greatmoor Brook | Culvert | BCL/CIV/0226 | Structural defect | 1) reposition displaced brickwork on H/M downside wall. 2) Cut down tree and treat to prevent regrowth on L/M upside wall. | Bridge failure after prolongued deterioration | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) reposition displaced brickwork on H/M downside wall. 2) Cut down tree and treat to prevent regrowth on L/M upside wall. | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Bridge failure after prolongued deterioration | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 119.0924 | 119.0924 | Up & Down | 20A | Greatmoor Brook Bridge UB | Underbridge | BCL/CIV/0150 | Detailed Exam Required | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Unknown defects could affect line operation | Asset Management | All | Track patrol | 1 | 3 | 4 | 2018-04-11 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 | ref: BCL/CIV/0226 | Closed | D Gent | 2018-08-01
|  |  | GSM4 | 119.1188 |  | Both | 20 | Melton Road | Underbridge | BCL/CIV/0248 | Structural defect | 1) Assess upside main girder and 6ft rail bearer bottom flange due to buckles (bridge strike) 2) Replace incorrect telephone number on bridge strike plate 3)re-instate a safe track access point | 1) bridge could be under-capacity 2)Bridge strikes go unreported 3)injury to bridge strike inspection staff | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) Assess upside main girder and 6ft rail bearer bottom flange due to buckles (bridge strike) 2) Replace incorrect telephone number on bridge strike plate 3) Install collision protection beam (not priced here) | 1 | 1 | 2 | 2019-04-01 |  | Closed | Network Rail | 2019-04-01 | Bridge strikes go unreported | Track patrol and annual visual inspection | Network Rail |  |  | 2019-02-07
|  |  | GSM4 | 119.1188 | 119.1188 | Up & Down | 20 | Melton Road Bridge UB | Underbridge | BCL/CIV/0151 | Unrecorded structure defects | Low Bridge which is frequently struck. Collision protection beam? | Unknown defects could affect line operation | Asset Management | All | Track patrol | 3 | 1 | 4 | 2018-04-11 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 | Ref: BCL/CIV/0248 | closed | D Gent | 2018-08-01
|  |  | GSM4 | 119.1188 | 119.1188 | Up & Down | 20 | Melton Road Bridge UB | Underbridge | BCL/CIV/0152 | Defects from previous detailed exam | Structural defect | deterioration of structure | Asset Management | Passengers & Workforce | Annual vissual inspection req | 3 | 1 | 4 | 2018-04-26 |  |  |  |  | 1) Assess upside main girder and 6ft rail bearer bottom flange due to buckles (bridge strike) 2) Replace incorrect telephone number on bridge strike plate | 1 | 1 | 2 | 2018-06-01 | Ref: BCL/CIV/0248 | closed | D Gent | 2018-06-01
|  |  | GSM4 | 119.1188 | 119.1188 | Up & Down | 20 | Melton Road Bridge UB | Underbridge | BCL/CIV/0163 | Multiple bridge strikes | Structural defect | deterioration of structure | Asset Management | Passengers & Workforce | Annual vissual inspection req | 3 | 3 | 6 | 2018-08-28 |  |  |  |  | Carry out structural assessment in accordance with CIV/025 to determine effects of structural defects on load carrying capacity and residual life. | 1 | 1 | 2 | 2019-04-01 | Ref: BCL/CIV/0248 | closed | D Gent | 2018-11-01
|  |  | GSM4 | 119.1408 | 119.1408 |  | 19B BRICK CULVERT |  | Culvert | BCL/CIV/0153 |  | No records available | May be unrecorded defects which are not receiving attention or listed in the work bank. Risk to operation of the line | Safety | Workforce | Track patrol | 1 | 3 | 4 | 2018-04-12 |  |  |  |  | visual inspection req 2018 Exam completed, no significant defects recorded | 1 | 1 | 2 | 2019-04-01 | Annual exam report | closed | D Gent | 2019-04-01
|  |  | GSM4 | 119.1628 | 119.1628 |  | 19A BRICK CULVERT |  | Culvert | BCL/CIV/0154 | Displaced/dropped brickwork | Structural defect | Further deterioration of structure | Asset Management | Workforce | Track patrol | 2 | 3 | 5 | 2018-04-26 |  |  |  |  | Fix/recase Displaced/dropped brickwork | 1 | 1 | 2 | 2019-04-01 | Ref: BCL/CIV/0224 | closed | D Gent | 2019-04-01
19A | 52.9037 | -1.1139 | GSM4 | 119.1628 |  |  | 19A | Culvert | Culvert | BCL/CIV/0224 | Structural defect | Fix/recase Displaced/dropped brickwork | Bridge failure after prolongued deterioration | Asset Management | All | Track patrol and annual visual inspection | 2 | 2 | 4 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Fix/recase Displaced/dropped brickwork | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Bridge failure after prolongued deterioration | Track patrol and annual visual inspection | Network Rail
19C | 52.9037 | -1.1139 | GSM4 | 119.1694 |  |  | 19C | Lings Bar | Underbridge | BCL/CIV/0225 | Structural defect | Graffiti on bridge ID sign. Sign appears to state structure is 19A - this structure is believed to be 19C - please replace sign with correct information. | Misidentification of structure | Asset Management | All | Track patrol and annual visual inspection | 2 | 2 | 4 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Graffiti on bridge ID sign. Sign appears to state structure is 19A - this structure is believed to be 19C - please replace sign with correct information. | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Misidentification of structure | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 119.1694 | 119.1694 | Up & Down | 19C | Lings Bar UB | Underbridge | BCL/CIV/0155 | Unrecorded structure defects | Limited clearance both lines, no limited clearance signs | Unknown defects could affect line operation | Asset Management | All | Track patrol | 1 | 3 | 4 | 2018-04-11 |  |  |  |  | Carry out inspection in the first instance to determine level of risk | 1 | 2 | 3 | 2018-08-01 | Ref: BCL/CIV/0225 | closed | D Gent | 2018-08-01
|  |  | GSM4 | 119.1694 | 119.1694 | Up & Down | 19C | Lings Bar UB | Underbridge | BCL/CIV/0156 | Defects from previous detailed exam | Structural defect | deterioration of structure | Asset Management | Passengers & Workforce | Annual vissual inspection req | 3 | 1 | 4 | 2018-04-26 |  |  |  |  | Graffiti on bridge ID sign. Sign appears to state structure is 19A - this structure is believed to be 19C - please replace sign with correct information. | 1 | 1 | 2 | 2018-06-01 | Ref: BCL/CIV/0225 | closed | D Gent | 2018-06-01
19 | 52.7557 | -0.93016 | GSM4 | 119.1738 |  |  | 19 | Gadds | Underbridge | BCL/CIV/0232 | Structural defect | 1) Recase missing bricks to barrel & L/M downside. 2) Point up and date tab transverse fracture to barrel. 3) Point up and date tab vertical fracture to upside spandrel/parapet wall. 4) Replace deteriorated fence at 4 corners of structure. | Injury to personnel | Safety/ Health/ Environment | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Treat | 1) Recase missing bricks to barrel & L/M downside. 2) Point up and date tab transverse fracture to barrel. 3) Point up and date tab vertical fracture to upside spandrel/parapet wall. 4) Replace deteriorated fence at 4 corners of structure. | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Injury to personnel | Track patrol and annual visual inspection | Network Rail
|  |  | GSM4 | 119.1758 | 119.1758 | Up & Down | 19 | Gadd's Bridge UB | Underbridge | BCL/CIV/0157 | Defects from previous detailed exam | Structural defect | deterioration of structure | Asset Management | Passengers & Workforce | Annual vissual inspection req | 3 | 1 | 4 | 2018-04-26 |  |  |  |  | Next Detailed - 2021 1) Recase missing bricks to barrel & L/M downside. 2) Point up and date tab transverse fracture to barrel. 3) Point up and date tab vertical fracture to upside spandrel/parapet wall. 4) Replace deteriorated fence at 4 corners of structure. | 1 | 1 | 2 | 2018-06-01 | Ref: BCL/CIV/0232 | closed | D Gent | 2018-06-01
27 | 52.8855 | -1.086 | GSM4 | 118.0374 |  |  | 27 | Keyworth Lane | Underbridge | BCL/CIV/0229 | Structural defect | Install new ID plate, remove bridge strike H-frame and re-paint | Misidentification of structure | Safety | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) Install new ID plate - strrike plates replaced on 8/2/19 2) remove timber height restriction signage to road-side spandrels and replace with painted lane-width restriction indicators | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Misidentification of structure | Track patrol and annual visual inspection | Network Rail
20 | 52.9001 | -1.1095 | GSM4 | 119.1188 |  | Both | 20 | Melton Road | Underbridge | BCL/CIV/0248 | Structural defect | 1) Assess upside main girder and 6ft rail bearer bottom flange due to buckles (bridge strike) 2) Replace incorrect telephone number on bridge strike plate 3)re-instate a safe track access point | 1) bridge could be under-capacity 2)Bridge strikes go unreported 3)injury to bridge strike inspection staff | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-11-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | 1) Assess upside main girder and 6ft rail bearer bottom flange due to buckles (bridge strike) 2) Replace incorrect telephone number on bridge strike plate - strrike plates replaced on 8/2/19 3) Install collision protection beam (not priced here) | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01 | Bridge strikes go unreported | Track patrol and annual visual inspection | Network Rail
24A | 52.8888 | -1.0928 | GSM4 | 118.099 |  | Side of track | 24A | Bradmore Lane | Culvert | BCL/CIV/0255 | Safety Defect | Missing safety fences to both headwalls; Heavy vegetation; Identified by NR inspection dated: January 2019 | Injury due to falling into culvert; Drainage system blocked due to vegetation | Safety/ Health/ Environment | All | None | 2 | 2 | 4 | 2019-02-18 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Install sfaety fences; Remove vegetation | 1 | 1 | 2 | 2019-04-01 |  | Open | Network Rail | 2019-04-01
|  |  | GSM4 | [10 empty] | Safety/ Health/ Environment | All |  |  |  | 0 | [8 empty] | 0
|  |  | GSM4 | [10 empty] | Safety/ Health/ Environment | All |  |  |  | 0 | [8 empty] | 0
|  |  | GSM4 | [10 empty] | Safety/ Health/ Environment | All |  |  |  | 0 | [8 empty] | 0
|  |  | GSM4 | [10 empty] | Safety/ Health/ Environment | All |  |  |  | 0 | [8 empty] | 0
|  |  | GSM4 | [10 empty] | Safety/ Health/ Environment | All |  |  |  | 0 | [8 empty] | 0
|  |  | GSM4 | [10 empty] | Safety/ Health/ Environment | All |  |  |  | 0 | [8 empty] | 0
|  |  | GSM4 | [10 empty] | Safety/ Health/ Environment | All |  |  |  | 0 | [8 empty] | 0
|  |  | GSM4 | [10 empty] | Safety/ Health/ Environment | All |  |  |  | 0 | [8 empty] | 0
|  |  | GSM4 | [10 empty] | Safety/ Health/ Environment | All |  |  |  | 0 | [8 empty] | 0
|  |  | GSM4 | [10 empty] | Safety/ Health/ Environment | All |  |  |  | 0 | [8 empty] | 0
|  |  | GSM4 | [10 empty] | Safety/ Health/ Environment | All |  |  |  | 0 | [8 empty] | 0
|  |  | GSM4 | [10 empty] | Safety/ Health/ Environment | All |  |  |  | 0 | [8 empty] | 0
|  |  | GSM4 | [10 empty] | Safety/ Health/ Environment | All |  |  |  | 0 | [8 empty] | 0
Note on K1: Guidance Adopt a meaningful numbering system to refer to hazards e.g. BR001, BR002 etc.
Note on L1: Guidance Clearly define the scenario where a hazard could be presented.
Note on M1: Guidance Clearly define the hazard in the context of the scenario.
Note on N1: Guidance Clearly describe the direct consequence that hazard introduces.
Note on O1: Guidance Identify the consequence category using the categories defined within the CRAM tab.
Note on P1: Guidance Identify who is at risk. Choose whether to adopt a broad approach (Passengers, Public, Workforce or a combination of the three) or specific (e.g. Train driver, lineside neighbours)
Note on Q1: Guidance Clearly identify the measures in place to either control the hazard or mitigate the consequences
Note on R1: Guidance Assess the risk with the current measures in place. Definitions for Consequence (Impact) and Likelihood can be found in the CRAM tab. In the Risk column, add up Consequence and Likelihood values.
Note on Z1: Guidance Identify further risk reduction measures required to be in place so that the risk is reduced to an acceptable level.
Note on AA1: Guidance Reassess the risk in light of the further measures using the criteria set out in the CRAM tab.
Note on AE1: Guidance Use this section to document progress on risk reduction measures.
Note on AF1: Guidance Identify whether all actions have been signed off, approved and implemented. This is only Closed when all actions are fully complete.
Note on AG1: Guidance Clearly identify an accountable owner for implementation of actions required and set a due date for completion.
Note on AI1: Guidance Clearly describe the residual hazard following the completion of all risk reduction measures, using principles of risk acceptance.
Note on AJ1: Guidance Clearly describe the control measures for the residual hazard documented.
Note on AK1: Guidance Clearly identify an accountable owner for the residual hazard.
Note on AL1: Guidance: Details of status of hazard when residual risk is being transferred to identified owner. No entry required until hazard is formally offered to residual risk owner.
Note on V2: Guidance Indicate the type of risk assessment methodology that is acceptable. Look at this in combination with H applied against C and B
Note on W2: Guidance Indicate the acceptable risk assessment principle.
Note on X2: Guidance Use this section to provide evidence to support selected principle.

## 2019_ESS Review
ELR | From | To | Track | Features /Identification/Local Name |  | Asset Type | Hazard Ref. | Description of Scenario | Description of Identified Hazard | Description of Consequence | Consequence Category | Persons at Risk | Current Risk Reduction Measures | Current Risk |  |  |  | CSM-RA Principle |  |  |  | Proposed Alternative Risk Reduction Measures | Target Risk |  |  |  | Evidence | Status (Open/Closed) | Risk Reduction Action Plan |  | Residual Hazard Description | Residual Hazard Control Measures | Residual Hazard Owner | Project Transfer Status | Work Arising Estimate | Actual Date | OS Reference
| Miles | Miles | [11 empty] | Liklihood | Severity | Rating | Date Logged | Qualitative / Quantitative result or N/A | Applicable risk criteria | Evidence (e.g. NR Standard (including sub-clause) | Treat (Reduce)/ Tolerate (Accept)/ Transfer (Share or Transfer)/ Terminate (Avoid) |  | Liklihood | Severity | Rating | Target Date |  |  | Action Plan Owner | Due Date
GSM4 | 106.1452 | 106.1452 | Both | 61 | RBE_ASFORDBY ROAD | Overbridge |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | No electrification within this structure | 1 | 3 | 4 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Tolerate |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 108.022 | 108.022 | Both | 56 | Gravel Hole Bridge | Overbridge |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | None - Parapets are not at an adequate height for the required length above OLE equipment | 3 | 3 | 6 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Treat |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 108.0814 | 108.0814 | Both | 55 | Morris' Bridge | Overbridge |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | Parapets are of adequate dimensions to provide protection | 1 | 3 | 4 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Tolerate |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 110.0044 | 110.0132 | Both | 50 | Saxelbye Covered Way | Overbridge |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | None - Parapets are not at an adequate height for the required length above OLE equipment | 3 | 3 | 6 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Treat |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 112.121 | 112.121 | Both | 45 | Willoughby Road | Overbridge |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | Parapets are of adequate dimensions to provide protection | 1 | 3 | 4 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Tolerate |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 113.0198 | 113.0198 | Both | 44 | Wolley's Bridge | Overbridge |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | Parapets are of adequate dimensions to provide protection | 1 | 3 | 4 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Tolerate |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 113.0682 | 113.0682 | Both | 43 | Folly Hall Bridge | Overbridge |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | Parapets are of adequate dimensions to provide protection | 1 | 3 | 4 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Tolerate |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 114.1672 | 114.1672 | Both | 37 | Hollingworth's Bridge | Overbridge |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | Parapets are of adequate dimensions to provide protection | 1 | 3 | 4 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Tolerate |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 115.0484 | 115.0484 | Both | 36 | Widmerpool Station | Overbridge |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | Parapets are of adequate dimensions to provide protection | 1 | 3 | 4 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Tolerate |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 115.0858 | 115.0858 | Both | 35 | Newbound's Bridge | Overbridge |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | None - Parapets are not at an adequate height for the required length above OLE equipment | 3 | 3 | 6 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Treat |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 117.0022 | 117.0022 | Both | 31 | Page's Bridge | Overbridge |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | Parapets are of adequate dimensions to provide protection | 1 | 3 | 4 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Tolerate |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 117.0132 | 117.0132 | Both | 30 | Holbook's Bridge | Overbridge |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | Parapets are of adequate dimensions to provide protection | 1 | 3 | 4 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Tolerate |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 117.0748 | 117.0748 | Both | 29 | Burton's Bridge | Overbridge |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | Parapets are of adequate dimensions to provide protection | 1 | 3 | 4 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Tolerate |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 106.1666 | 107.0309 | Both | 60 | Asfordby | Tunnel Bore |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | No electrification within this structure | 1 | 3 | 4 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Tolerate |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 108.0976 | 108.1517 | Both | 54 | Saxelby | Tunnel Bore |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | None - Parapets are not adequate for the required length above OLE equipment | 3 | 3 | 6 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Treat |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 110.0279 | 110.1586 | Both | 49 | Grimston | Tunnel Bore |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | None - Parapets are not adequate for the required length above OLE equipment | 3 | 3 | 6 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Treat |  |  |  | 0 |  |  | Open | Network Rail
GSM4 | 115.1643 | 106.1212 | Both | 32 | Stanton | Tunnel Bore |  | Electrocution of workforce or members of the public if reaching over parapet | Potentially insufficient electrical clearances | Electrocution | Safety/ Health/ Environment | All | None - Parapets are not adequate for the required length above OLE equipment | 3 | 3 | 6 | 2019-03-12 | Quantitative | Code of Practice | GL/RT1210 AC Energy Subsystem and Interfaces | Treat |  |  |  | 0 |  |  | Open | Network Rail
Note on H1: Guidance Adopt a meaningful numbering system to refer to hazards e.g. BR001, BR002 etc.
Note on I1: Guidance Clearly define the scenario where a hazard could be presented.
Note on J1: Guidance Clearly define the hazard in the context of the scenario.
Note on K1: Guidance Clearly describe the direct consequence that hazard introduces.
Note on L1: Guidance Identify the consequence category using the categories defined within the CRAM tab.
Note on M1: Guidance Identify who is at risk. Choose whether to adopt a broad approach (Passengers, Public, Workforce or a combination of the three) or specific (e.g. Train driver, lineside neighbours)
Note on N1: Guidance Clearly identify the measures in place to either control the hazard or mitigate the consequences
Note on O1: Guidance Assess the risk with the current measures in place. Definitions for Consequence (Impact) and Likelihood can be found in the CRAM tab. In the Risk column, add up Consequence and Likelihood values.
Note on W1: Guidance Identify further risk reduction measures required to be in place so that the risk is reduced to an acceptable level.
Note on X1: Guidance Reassess the risk in light of the further measures using the criteria set out in the CRAM tab.
Note on AB1: Guidance Use this section to document progress on risk reduction measures.
Note on AC1: Guidance Identify whether all actions have been signed off, approved and implemented. This is only Closed when all actions are fully complete.
Note on AD1: Guidance Clearly identify an accountable owner for implementation of actions required and set a due date for completion.
Note on AF1: Guidance Clearly describe the residual hazard following the completion of all risk reduction measures, using principles of risk acceptance.
Note on AG1: Guidance Clearly describe the control measures for the residual hazard documented.
Note on AH1: Guidance Clearly identify an accountable owner for the residual hazard.
Note on AI1: Guidance: Details of status of hazard when residual risk is being transferred to identified owner. No entry required until hazard is formally offered to residual risk owner.
Note on S2: Guidance Indicate the type of risk assessment methodology that is acceptable. Look at this in combination with H applied against C and B
Note on T2: Guidance Indicate the acceptable risk assessment principle.
Note on U2: Guidance Use this section to provide evidence to support selected principle.

## Top 5s
ELR | From | To | Track | Features /Identification/Local Name |  | Asset Type | Hazard Ref. | Description of Scenario | Description of Identified Hazard | Description of Consequence | Consequence Category | Persons at Risk | Current Risk Reduction Measures | Current Risk |  |  |  | CSM-RA Principle |  |  |  | Proposed Alternative Risk Reduction Measures | Target Risk |  |  |  | Evidence | Status (Open/Closed) | Risk Reduction Action Plan |  | Residual Hazard Description | Residual Hazard Control Measures | Residual Hazard Owner | Project Transfer Status
| Miles | Miles | [11 empty] | Liklihood | Severity | Rating | Date Logged | Qualitative / Quantitative result or N/A | Applicable risk criteria | Evidence (e.g. NR Standard (including sub-clause) | Treat (Reduce)/ Tolerate (Accept)/ Transfer (Share or Transfer)/ Terminate (Avoid) |  | Liklihood | Severity | Rating | Target Date |  |  | Action Plan Owner | Due Date
STRUCTURES
GSM4 | 107.1716 |  | Both | 57 | Houghton's Bridge | Underbridge | BCL/CIV/0245 | Bridge failure due to excessive vehicle loading | Bridge has been assessed as being RA10, but there is currently no vehicle restrictions and the line speed is 115mph in this section | Bridge deforms under loading leading to failure | Asset Management | All | Annual vissual inspection req | 2 | 3 | 5 | 2018-09-26 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Short term: axle weight of actuial traffic is 11tonnes Medium term: Carry out a more detailed assessment (previous was done using the L0 tool); | 1 | 1 | 2 | 2018-11-01 |  | Open | D Gent | 2018-12-01 | Bridge failure after prolongued deterioration | Track patrol and annual visual inspection | Network Rail
GSM4 | 108.0484 | 108.0484 | Both | 55B BRICK CULVERT |  | Culvert | BCL/CIV/0162 | Collapsed section | Safety defect | Failure of structure resulting in failure of track | Safety/ Health/ Environment | All | Track patrol | 3 | 2 | 5 | 2018-08-20 | Qualitative | Explicit Risk Estimation | This defect has been scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Repair collapsed section of culvert | 1 | 1 | 2 | 2019-04-01 |  | Open | D Gent | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
GSM4 | 108.22 |  | Both | 56 | Gravel Hole Bridge | Overbridge | BCL/CIV/0249 | Structural defect in barrel of Span 2 | 1) fractures to soffit; 2) Loose coping stone 3) Loose brickwork in soffit | Train or personnel struck, structural failure | Asset Management | All | Track patrol and annual visual inspection | 2 | 3 | 5 | 2018-12-14 | Qualitative | Explicit Risk Estimation | This defect has been risk scored in accordance with the NR CRAM as instructed by C Browne on 14/12/18. D Gent believes it requires more urgent attention | Tolerate | Monitoring by weekly track patrol until 01/02/2019, then daily monitoring by track patrol team throughout February and March (the anticipated periods of sustained freezing wetaher). Weatehr and temperature will be monitored and monitoring regime altared accordingly. Remedial works planned for early 2019 | 2 | 3 | 5 | 2018-12-14 |  | Open | Network Rail | 2019-04-01 | Train or personnel struck, structural failure | Track patrol and annual visual inspection | Network Rail
GSM4 | 113.0337 | 113.0337 | D/S | TT09.29 | OLE Structure | OLE Equipt. | BCL/CIV/0254 | Undermining of foundation | Foundation within embankment is being undermined - Identified by NR visual exam in 2018 | Collapse of structure and failure of OLE | Performance | All | Track patrol and annual visual inspection | 1 | 4 | 5 | 2019-01-21 | Qualitative | Explicit Risk Estimation | This defect has been identified by NR examination and scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Reinstate surrounding ground with concrete The foundation is likely to be a 4m long pile, in accordance with OLEMI details and therefore is not actually being undermined. | 1 | 1 | 2 | 2020-04-01 |  | Open | Network Rail | 2020-04-01 | Failure of structure | Track patrol and annual visual inspection | Network Rail
GSM4 | 113.0772 | 113.0772 | U/S | TT10.04 | OLE Strcuture | OLE Equipt. | BCL/CIV/0255 | Undermining of foundation | Foundation within embankment is being undermined - Identified by NR visual exam in 2018 | Collapse of structure and failure of OLE | Performance | All | Track patrol and annual visual inspection | 1 | 4 | 5 | 2019-01-21 | Qualitative |  | This defect has been identified by NR examination and scored in accordance with the NR CRAM V1.2 as instructed on the 14/12/2018 | Tolerate | Reinstate surrounding ground with concrete The foundation is likely to be a 4m long pile, in accordance with OLEMI details and therefore is not actually being undermined. | 1 | 1 | 2 | 2020-04-01 |  | Open | Network Rail | 2020-04-01 | Failure of structure | Track patrol and annual visual inspection | Network Rail
Total HAZIDS: |  | 220
Closed HAZIDS: |  | 166
Open HAZIDS: |  | 54
Map: |  | https://drive.google.com/open?id=1TOPn66xL_2owJKwHAvmDd2evhaeFHFPq&usp=sharing
Note on H1: Guidance Adopt a meaningful numbering system to refer to hazards e.g. BR001, BR002 etc.
Note on I1: Guidance Clearly define the scenario where a hazard could be presented.
Note on J1: Guidance Clearly define the hazard in the context of the scenario.
Note on K1: Guidance Clearly describe the direct consequence that hazard introduces.
Note on L1: Guidance Identify the consequence category using the categories defined within the CRAM tab.
Note on M1: Guidance Identify who is at risk. Choose whether to adopt a broad approach (Passengers, Public, Workforce or a combination of the three) or specific (e.g. Train driver, lineside neighbours)
Note on N1: Guidance Clearly identify the measures in place to either control the hazard or mitigate the consequences
Note on O1: Guidance Assess the risk with the current measures in place. Definitions for Consequence (Impact) and Likelihood can be found in the CRAM tab. In the Risk column, add up Consequence and Likelihood values.
Note on W1: Guidance Identify further risk reduction measures required to be in place so that the risk is reduced to an acceptable level.
Note on X1: Guidance Reassess the risk in light of the further measures using the criteria set out in the CRAM tab.
Note on AB1: Guidance Use this section to document progress on risk reduction measures.
Note on AC1: Guidance Identify whether all actions have been signed off, approved and implemented. This is only Closed when all actions are fully complete.
Note on AD1: Guidance Clearly identify an accountable owner for implementation of actions required and set a due date for completion.
Note on AF1: Guidance Clearly describe the residual hazard following the completion of all risk reduction measures, using principles of risk acceptance.
Note on AG1: Guidance Clearly describe the control measures for the residual hazard documented.
Note on AH1: Guidance Clearly identify an accountable owner for the residual hazard.
Note on AI1: Guidance: Details of status of hazard when residual risk is being transferred to identified owner. No entry required until hazard is formally offered to residual risk owner.
Note on S2: Guidance Indicate the type of risk assessment methodology that is acceptable. Look at this in combination with H applied against C and B
Note on T2: Guidance Indicate the acceptable risk assessment principle.
Note on U2: Guidance Use this section to provide evidence to support selected principle.

## Risk Matrix
Ref: Network Rail CRAM v1.2 received 30/11/2018
Impact area | 1 | 2 | 3 | 4 | 5
Safety/ Health/ Environment | Event with the potential for less than 20 minor injuries or a single major injury (less than .1 FWI) Minor health effects not affecting work performance or causing disability, treatment applied by First Aider onsite e.g. minor cuts & abrasions Negligible impact to a minimal area of low environmental significance, managed by internal control procedures (e.g. Spills <20 litres; Fly tipping) | Significant event with the potential of a single major injury to five major injuries (between .1 - .5 FWI) Minor health effects causing lost time injury 1-20 days with some impact on local level activities, e.g. MSK – musculoskeletal injury from manual handling with short term health issues Minor or minimal short-term impacts to the environment (e.g. Minor spill of >20 litres; dust/odour; Disturbance to locally protected Biodiversity Action Plan (BAP) species or its habitat) | Significant event with the potential of between five major injuries and two fatalities (between .5 and 2 FWI) Major health effects causing lost time injury 20+ days and/or redeployment, e.g. MSK with long term health issues, hand/arm vibration syndrome Significant impact to the wider environment, where short term (< 6 months) restoration works are needed (e.g. Confirmed spread of an invasive species; Disturbance to a statutorily protected site or a European/nationally protected species or habitat; Damage to a Site of Special Scientific Interest (SSSI); destroying the habitat of a protected species) | Catastrophic event with the potential of between two and 10 fatalities (between 2-10 FWI) Irreversible damage causing serious disability and more than 6 months off work or fatalities e.g. respirable crystalline silica (RCS) from ballast dust and asbestos from buildings to renewals Major, persistent and/or extensive impact to the environment where longer term remediation is required (> 6 months) e.g. Long term pollution involving toxic, hazardous or infectious materials/waste; Use of resources under threat of depletion; Damage to a statutorily protected site or a European / nationally protected species or habitat; Unlicensed killing of a small population of a European/ nationally protected species) | Catastrophic event with the potential of over 10 fatalities (10 FWI) Catastrophic health effects causing multiple fatalities from long term exposure in the work place e.g. silica and asbestos or effect of ill health on work e.g. sudden incapacity for a Lookout or Train Driver Catastrophic and irreversible environmental damage (e.g. Irreparable damage to protected sites and/or unlicensed killing of a local/regionally significant protected species population; Direct over- consumption of natural resources causing irreversible depletion of that resource)
Performance | Planned disruption for up to a day on any one route Project <1yr = <=1 week schedule delays Project >1yr = <=2 weeks <52hrs possession; overrun <=15mins 52hrs – week possession; overrun <=1hr 1-4week possession; overrun <= 4hrs | Unplanned disruption (for up to a day) on any one route Project <1yr = 1-2 weeks schedule delays Project >1yr = 2-4 weeks <52hrs possession; overrun 15 - 30 minute 52hrs – week possession; overrun 1-2hrs 1-4week possession; overrun 4-7hrs | Unplanned disruption (for up to a week) on any one route or Up to a day on multiple routes Project <1yr = 2-4weeks schedule delays Project >1yr = 4-8 weeks <52hrs possession; overrun 30min to 1hr 52hrs – week possession; overrun 2-4hrs 1-4week possession; overrun 7-14hrs | Unplanned disruption for over a week on multiple routes and limited access to station facilities Project <1yr = 4-6 weeks schedule delays Project >1yr = 8-12 weeks <52hrs possession; overrun 1 – 2hrs 52hrs – week possession; overrun 4-7hrs 1-4week possession; overrun 14-26hrs | All users experience prolonged and unplanned disruption to key routes. Access to major station facilities likely to be severely restricted Project <1yr = >6 weeks schedule delays Project >1yr = >12 weeks <52hrs possession; overrun >2 hrs 52hrs – week possession; overrun >7hrs 1-4week possession; overrun >26hrs
Finance | £0 - £2m OR Less than 3% of allocated budget Efficiency target 100% deliverable No Breach of cash limits | £2 - 10m OR between 3% - 5% of allocated budget Efficiency target >90% deliverable Minor breach of cash limits | £10 - 50m OR between 5% and 7% of allocated budget Efficiency target 80-90% deliverable Minor to moderate breach of cash limits to create minimum value | £50 - 250m OR between 7% and 10% of allocated budget Efficiency target 60-80% deliverable Moderate breach of cash limits where there is potential to create some value | Over £250m OR Greater than 10% of allocated budget Efficiency target <60% deliverable Significant breach of cash limit or where there is the potential to create significant value
Asset Management | Does not directly and adversely affect either railway infrastructure reliability or railway infrastructure condition Or Direct and adverse impact on railway infrastructure reliability or railway infrastructure condition is minimal Failure to achieve annual CRI target Failure to achieve annual contribution to the CSI target | Directly and adversely affects railway infrastructure reliability within the current performance year Or Directly and adversely affects railway infrastructure condition within the current control period Failure to deliver 50% CRI target value in year concerned Failure to achieve annual contribution by such a margin as this threatens CSI outturn for CP5 | Directly and adversely affects railway infrastructure reliability over the current and next performance year Or Directly and adversely affects railway infrastructure condition over the current & next control period Failure to improve CRI target value in Control Period (or 5 yr period) Failure to achieve CSI in CP5 | Directly and adversely affects railway infrastructure reliability over the next 3-4 performance years Or Directly and adversely affects railway infrastructure condition over the next three control periods (11+ years) Deterioration in CRI between 10% to 49% in Control Period (or 5 yr period) – (against target) Failure by up to 0.5% to deliver CSI in CP5 | Directly and adversely affects railway infrastructure reliability over the next 5+ performance years Or Directly and adversely affects railway infrastructure condition over the next four control periods (16+ years) Deterioration in CRI by > 50% in Control Period (or 5 yr period) - (against target) A major shortfall in CSI by >0.5% in CP5
Satisfaction & Reputation | Short-term adverse local stakeholder reaction Short term loss of morale with poor performance of non-critical activities Minor legal issues, non-compliance or breach of regulation. Legal challenge, minor out of court settlement limited to parties involved and expected outcome known No ORR action. | Adverse local media reports over a period. Localised stakeholder concern. Minor disengagement. Effectiveness / Efficiency compromised with service failures in non-critical activities Breach of regulation with investigation or report to authority with prosecution and/or moderate fine possible. Limited to parties involved but outcome uncertain Risk scores a 1 – 2 on the ORR regulatory escalator | Significant local and / or regional reports including social media. National media interest creating public concern. Negative national stakeholder statements from both government departments and/or TOC/FOCs. Some disengagement leading to effectiveness / efficiency compromised in some critical activities. Serious breach of regulation. Major litigation/ Class action/ criminal prosecution/prohibition notice. Local profile and outcomes uncertain. Risk scores a 3 on the ORR regulatory escalator | Extensive prolonged diverse national reporting and public disputes with key stakeholders, e.g. breakdown of a TOC alliance. A major downturn in company-wide engagement leading to service failures within some critical activities. Significant prosecution and fines. Very serious litigation including class actions. National profile, impact on current/future business operations. Risk scores a 4 on the ORR regulatory escalator | Extensive and prolonged negative reporting nationally or public disputes with key stakeholders, including political and/or TOC/FOCs. Escalation to external bodies inevitable & impossible to contain in medium term. Potential for significant changes imposed on NR, its responsibilities and structure A significant downturn in companywide engagement. Serious failings across most services National profile, major impact on current and future business operation. Prosecution likely. Potential prison terms for executives and/or high fines for organisation. Multiple litigations. Risk scores 5 on the ORR regulatory escalator
Liklihood | 1 | 2 | 3 | 4 | 5
Criteria | <5% Very Low likelihood the risk will occur Risk would occur less than once in 25 years | 5 – 20% Low likelihood the risk will occur Risk would occur between once in 25 years or up to once in 5 years | 21 – 50% Medium likelihood the risk will occur Risk would occur between once in 5 years to just less than once a year | 51 – 75% High likelihood the risk will occur Risk would occur between 1 and 5 times a year | >75% Very High likelihood the risk will occur Risk would occur 5 times a year or more
Severity
Applicable risk criteria |  | Persons at Risk |  | Structure type |  |  |  | 1 | 2 | 3 | 4 | 5
Code of Practice |  | Passengers |  | 25kV sub |  | Liklihood | 1 | 2 | 3 | 4 | 5 | 6 | Acceptable | 1 - 5
Reference System |  | Members of public (MoP) |  | Access point |  |  | 2 | 3 | 4 | 5 | 6 | 7 | Consider reasonably practicable improvements | 6
Explicit Risk Estimation |  | Workforce |  | Adjustment Switch |  |  | 3 | 4 | 5 | 6 | 7 | 8 | Consider practical improvements | 7
|  | Workforce Health & Safety |  | Building |  |  | 4 | 5 | 6 | 7 | 8 | 9 | Unacceptable | 8 - 9
|  | Passengers & MoP |  | CCTV System |  |  | 5 | 6 | 7 | 8 | 9 | 10 | Intolerable | 10
|  | Passengers & Workforce |  | Cross Over
|  | MoP & Workforce |  | Culvert
|  | All |  | DC Substation
Elec Supply Point
Fence
Insulated Block Joint
Lifting Equipment
Marker Post
OLE Equipt.
OLE Structure
Open drain
Overbridge
Pipe
Point Clamp
Point Elec
Point Hand
Point Mech
Pway
Radio Mast
Retaining Wall
S&C
Side of line Bridge
Shore Supply DC
Sign
Switchgear
Structure
Track ID
Track drainage
Train Stop
Transformer
Tunnel Bore
Tunnel Shaft
Underbridge
UTX
Vegetation
Wire Run

## RAM Info
Structure Type | Department | East Mids Contact | East Mids CC
Bridges and Tunnels | Structures | Martin.Wainwright@networkrail.co.uk
Complex Gantry | Signalling | Andrew.Little@networkrail.co.uk | EMR&ESP&C@networkrail.co.uk
Simple Signal Posts and Other Structures | Signalling | Andrew.Little@networkrail.co.uk | EMR&ESP&C@networkrail.co.uk
Lineside Box Supports | Signalling | Andrew.Little@networkrail.co.uk | EMR&ESP&C@networkrail.co.uk
Simple OLE Structure | E&P | Sam.Black@networkrail.co.uk | David.a.Johnson@networkrail.co.uk
Feeder Station Support | E&P | Sam.Black@networkrail.co.uk | David.a.Johnson@networkrail.co.uk
Lighting Support Structures | E&P | mark.davies3@networkrail.co.uk
Metallic Lattice Support | E&P | mark.davies3@networkrail.co.uk
Timber Posts - Lighting | E&P | mark.davies3@networkrail.co.uk
CCTV Support | Telecoms | Sam.Black@networkrail.co.uk
Simple Radio Mast | Telecoms | John.ARMSTRONG@networkrail.co.uk
GSMR Masts | Telecoms | John.ARMSTRONG@networkrail.co.uk
Timber Posts - Telecoms | Telecoms | John.ARMSTRONG@networkrail.co.uk